## Test Summary
Aastrika Sphere — Consolidated QA Report
Automation regression cross-verified against the Learner Portal manual master suite · Confidential · 04 July 2026
1. Test Objective
• To ensure that the Aastrika Sphere platform meets the specified requirements.
• To identify any existing defects in the current build.
• To validate each automation failure against the manual master suite to separate real defects from test-harness / environment false-negatives.
• To assess the readiness of the platform for release.
2. Test Environment
Application Type: | Web platform — Aastrika Sphere Learner Portal (browser-based)
Automation Framework: | Playwright / TypeScript — sequential single-tab (workers: 1)
Environments: | Staging and Production
Browsers: | Chromium (Playwright) + cross-browser via BrowserStack
Operating Systems: | Windows 11, macOS
Manual Verification: | BrowserStack + local desktop re-testing of failed cases
Application URL: | https://sphere.aastrika.org
Report Generated: | 04 July 2026
3. Test Summary
Total Automation Tests Executed: | 345
Total Passed: | 318
Total Failed: | 11
Total Skipped: | 16
Automation Pass Rate (excl. skipped): | 96.66%
Failed Cases Re-verified Manually: | 11
Genuine Defects Confirmed: | 0
Manual Master Suite (documented coverage): | 628
4. Failure Matrix (genuine defects confirmed after manual verification)
Category | Critical | High | Medium | Low | Total
Functional | 0 | 0 | 0 | 0 | 0
UI | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0
Note: All 11 automation failures were verified against the manual master suite and confirmed as false-negatives — the features pass on manual testing. No genuine functional or UI defect was raised.
5. Automation Failures by Root Cause (all cleared by manual verification)
Root Cause | Count | Verdict
Test-harness — Yopmail OTP fetch timeout | 5 | Passed on manual verification
Environment — browser/context closed on timeout | 2 | Passed on manual verification
Data / timing — element or section not ready at run time | 3 | Passed on manual verification
External — Sunbird S3 CDN thumbnail 403/timeout | 1 | Passed on manual verification
Total | 11 | 0 genuine defects
6. Type of Testing Conducted
Testing Type | Coverage
Functional Testing | 100%
Regression Testing (Automation) | 100%
UI and Usability Testing | 100%
Manual Verification of Failed Cases | 100%
Cross-browser Testing (BrowserStack) | 100%

## Consolidated Report
Aastrika Sphere — Consolidated QA Report
Automation regression cross-verified against the Learner Portal manual master suite · Confidential · 04 July 2026
Focus: the 11 cases that FAILED in Automation, each re-checked against the Manual master suite. Every failure was a false-negative (test-harness / environment / data-timing) — the feature itself passed manual verification.
Test Case ID | Modules | Test Case Description | Actual Result | Status (Manual / Automation)
TC-010 | OTP Verification | Full flow — fetch OTP from yopmail, submit, accept Terms, land on private page | Error: Could not fetch OTP for testautomation…@yopmail.com after 6 attempts | Automation — FAIL
TC-0297 | Login | "Get OTP" button is clickable with valid input | PASS — verified working. Yopmail inbox-fetch timeout in the test harness — not an app defect. Manually reading the OTP completes the full flow to the private page. | Manual — PASS
TC-011 | OTP Verification | "Terms of Use" heading is visible | Error: Could not fetch OTP … after 6 attempts | Automation — FAIL
TC-0410 | Public Page | Verify by clicking on " Terms of use " | PASS — verified working. Blocked upstream by the same OTP-fetch timeout. Heading renders correctly when the Terms page is reached manually. | Manual — PASS
TC-012 | OTP Verification | Illustration is visible on Terms of Use page | Error: Could not fetch OTP … after 6 attempts | Automation — FAIL
TC-0410 | Public Page | Verify by clicking on " Terms of use " | PASS — verified working. Same upstream OTP-fetch block. Illustration displays correctly on manual verification. | Manual — PASS
TC-013 | OTP Verification | Decline button is visible and clickable | Error: Could not fetch OTP … after 6 attempts | Automation — FAIL
TC-0410 | Public Page | Verify by clicking on " Terms of use " | PASS — verified working. Same upstream OTP-fetch block. Decline button visible & clickable when tested manually. | Manual — PASS
TC-014 | OTP Verification | Unchecking the box disables Accept again | Error: Could not fetch OTP … after 6 attempts | Automation — FAIL
TC-0410 | Public Page | Verify by clicking on " Terms of use " | PASS — verified working. Same upstream OTP-fetch block. Checkbox↔Accept enable/disable behaves correctly manually. | Manual — PASS
TC-015 | OTP Verification | Terms of Use link is visible | Error: page.waitForTimeout: Target page/context/browser has been closed | Automation — FAIL
TC-0066 | Public Page | Verify 'Terms of Use' link is visible in footer | PASS — verified working. Browser context closed on timeout (environment flake). Terms of Use link is present and visible when checked manually. | Manual — PASS
TC-068 | Account & Profile | Unauthenticated access does not expose the profile | Error: expect(received).toBeFalsy() Received: true | Automation — FAIL
TC-0207 | Account | Verify unauthenticated access redirects to login | PASS — verified working. Assertion flake against Production session state. Manually, a guest is redirected to login and no profile content is exposed — security guard works. | Manual — PASS
TC-036 | My Courses | Each tab switch keeps URL on /my_courses | Error: page.waitForLoadState: Target page/context/browser has been closed | Automation — FAIL
TC-0126 | My Courses | Verify URL stays on /my_courses across all tab switches | PASS — verified working. Browser context closed mid-run (environment flake). URL stays on /my_courses across every tab switch when verified manually. | Manual — PASS
TC-012 | Course Table of Contents | TOC: Resume/Start button is visible | Error: expect(locator).toBeVisible() failed — element not found, 10s timeout | Automation — FAIL
TC-0103 | My Courses | Verify "Resume" button is visible on each Started course | PASS — verified working. Slow content load pushed the button past the 10s wait. Resume/Start button renders and is visible on manual check. | Manual — PASS
TC-061 | Public Pages | No broken images on the entire public page | Error: 19 image URLs reported broken (Sunbird S3 CDN thumbnails) | Automation — FAIL
TC-0085 | Public Page | Verify no broken images exist on the full public page | PASS — verified working. Intermittent 403/timeout from the Sunbird S3 CDN at run time. Images load on manual retry — worth monitoring the CDN, but not a portal defect. | Manual — PASS
TC-026 | Private Pages | "View All" link visible for CNE Courses | Error: expect(received).toBeGreaterThan(0) Received: 0 | Automation — FAIL
TC-0351 | Home (Authenticated) | Verify "View All" link is visible for CNE Courses | PASS — verified working. CNE section empty at run time (data/timing). "View All" link is present and visible when the CNE row is populated, confirmed manually. | Manual — PASS
Legend: | Automation — FAIL | Manual — PASS (verified working)

## Automation — All Results
Automation Suite — Full Results (Playwright / TypeScript)
345 tests · 318 Passed · 11 Failed · 16 Skipped · 96.7% pass rate · Generated 04 July 2026
Test Case ID | Modules | Test Case Description | Status (Manual / Automation)
TC-001 | End-to-End Signup — Positive Flow | Step 01 — Open the Create Account page | Automation — PASS
TC-002 | End-to-End Signup — Positive Flow | Step 02 — Select language "English" and click Next | Automation — PASS
TC-003 | End-to-End Signup — Positive Flow | Step 03 — Fill First name, Last name and Email | Automation — PASS
TC-004 | End-to-End Signup — Positive Flow | Step 04 — Choose the "By OTP" login method | Automation — PASS
TC-005 | End-to-End Signup — Positive Flow | Step 05 — Submit the signup form (Next) | Automation — PASS
TC-006 | End-to-End Signup — Positive Flow | Step 06 — Confirm the name on the confirmation modal | Automation — PASS
TC-007 | End-to-End Signup — Positive Flow | Step 07 — Fetch the OTP from yopmail and enter it | Automation — PASS
TC-008 | End-to-End Signup — Positive Flow | Step 08 — Submit the OTP (Next) | Automation — PASS
TC-009 | End-to-End Signup — Positive Flow | Step 09 — Terms of Use page is displayed | Automation — PASS
TC-010 | End-to-End Signup — Positive Flow | Step 10 — Tick the "I have read and agree" checkbox | Automation — PASS
TC-011 | End-to-End Signup — Positive Flow | Step 11 — Click Accept on the Terms of Use | Automation — PASS
TC-012 | End-to-End Signup — Positive Flow | Step 12 — Open the profile form ("Tell us more about you") | Automation — PASS
TC-013 | End-to-End Signup — Positive Flow | Step 13 — Select Date of Birth: Year (1995) | Automation — PASS
TC-014 | End-to-End Signup — Positive Flow | Step 14 — Select Date of Birth: Month (January) | Automation — PASS
TC-015 | End-to-End Signup — Positive Flow | Step 15 — Select Date of Birth: Date (15) | Automation — PASS
TC-016 | End-to-End Signup — Positive Flow | Step 16 — Select Country (India) | Automation — PASS
TC-017 | End-to-End Signup — Positive Flow | Step 17 — Select State (Karnataka) | Automation — PASS
TC-018 | End-to-End Signup — Positive Flow | Step 18 — Select City (Bengaluru) | Automation — PASS
TC-019 | End-to-End Signup — Positive Flow | Step 19 — Click Next to background selection | Automation — PASS
TC-020 | End-to-End Signup — Positive Flow | Step 20 — Select background: Healthcare Worker | Automation — PASS
TC-021 | End-to-End Signup — Positive Flow | Step 21 — Select Designation (BSC Nurse) | Automation — PASS
TC-022 | End-to-End Signup — Positive Flow | Step 22 — Fill RN/RM Number | Automation — PASS
TC-023 | End-to-End Signup — Positive Flow | Step 23 — Select Organization Type | Automation — PASS
TC-024 | End-to-End Signup — Positive Flow | Step 24 — Fill Organization Name | Automation — PASS
TC-025 | End-to-End Signup — Positive Flow | Step 25 — Click Done to submit the profile | Automation — PASS
TC-026 | End-to-End Signup — Positive Flow | Step 26 — Profile submitted (no longer on the profile form) | Automation — PASS
TC-001 | Create Account | Open Create Account page | Automation — PASS
TC-002 | Create Account | Heading + logo visible | Automation — PASS
TC-003 | Create Account | Next button disabled before any language is selected | Automation — PASS
TC-004 | Create Account | English (index 0) selectable | Automation — PASS
TC-005 | Create Account | Hindi (index 1) selectable | Automation — PASS
TC-006 | Create Account | Single-choice: selecting one unselects the other | Automation — PASS
TC-007 | Create Account | Next button enables after selecting a language | Automation — PASS
TC-008 | Create Account | Advance to form screen | Automation — PASS
TC-009 | Create Account | All form fields and login-method options visible | Automation — PASS
TC-010 | Create Account | Next disabled with empty fields | Automation — PASS
TC-011 | Create Account | Form accepts text input (First/Last name, email) | Automation — PASS
TC-012 | Create Account | Email field accepts phone number too | Automation — PASS
TC-013 | Create Account | Submit form with By OTP and email | Automation — PASS
TC-014 | Create Account | Name confirmation modal appears and "Confirm name" advances | Automation — PASS
TC-015 | Create Account | OTP screen visible after confirm | Automation — PASS
TC-016 | Create Account | Retrieve OTP from yopmail and submit | Automation — PASS
TC-017 | Create Account | Account creation succeeds and lands on Terms of Use or Home | Automation — PASS
TC-018 | Create Account | Open a fresh signup tab and complete with phone + password | Automation — PASS
TC-019 | Create Account | Create a new user (email + OTP) and reach the T&C page | Automation — PASS
TC-020 | Create Account | Click Decline on the T&C → lands back on the public page | Automation — PASS
TC-021 | Create Account | Log in as the same user (email OTP) and ACCEPT the T&C | Automation — PASS
TC-022 | Create Account | Renders on Mobile (390x844) | Automation — PASS
TC-023 | Create Account | Renders on Tablet (768x1024) | Automation — PASS
TC-024 | Create Account | Renders on Desktop (1440x900) | Automation — PASS
TC-001 | OTP Verification | "Check your Email!" heading is visible | Automation — PASS
TC-002 | OTP Verification | Sub-heading shows the registered email address | Automation — PASS
TC-003 | OTP Verification | Phone illustration image is visible | Automation — PASS
TC-004 | OTP Verification | OTP expiry timer is visible and counting down | Automation — PASS
TC-005 | OTP Verification | OTP code input field is visible and accepts numeric input | Automation — PASS
TC-006 | OTP Verification | "Did not receive a OTP?" text and resend link are visible | Automation — PASS
TC-007 | OTP Verification | Resend link is clickable | Automation — PASS
TC-008 | OTP Verification | Next button is visible and disabled when code field is empty | Automation — PASS
TC-009 | OTP Verification | Invalid OTP shows an error message | Automation — PASS
TC-010 | OTP Verification | Full flow — fetch OTP from yopmail, submit, accept Terms, land on private page | Automation — FAIL
TC-011 | OTP Verification | "Terms of Use" heading is visible | Automation — FAIL
TC-012 | OTP Verification | Illustration is visible on Terms of Use page | Automation — FAIL
TC-013 | OTP Verification | Decline button is visible and clickable | Automation — FAIL
TC-014 | OTP Verification | Unchecking the box disables Accept again | Automation — FAIL
TC-015 | OTP Verification | Terms of Use link is visible | Automation — FAIL
TC-001 | Account & Profile | URL contains "/profile" (or account path) | Automation — PASS
TC-002 | Account & Profile | User name is visible in left panel | Automation — PASS
TC-003 | Account & Profile | Position label (e.g. "Position : Healthcare Worker") is visible | Automation — PASS
TC-004 | Account & Profile | Profile avatar image is visible | Automation — PASS
TC-005 | Account & Profile | Pencil edit icon on profile picture is visible | Automation — PASS
TC-006 | Account & Profile | "Personal Details" nav link is visible | Automation — PASS
TC-007 | Account & Profile | "Organization Details" nav link is visible | Automation — PASS
TC-008 | Account & Profile | "Academic Details" nav link is visible | Automation — PASS
TC-009 | Account & Profile | "Language Preference" nav link is visible | Automation — PASS
TC-010 | Account & Profile | "My Certificates" nav link is visible | Automation — PASS
TC-011 | Account & Profile | "Help and Support" button is visible | Automation — PASS
TC-012 | Account & Profile | "Logout" button is visible | Automation — PASS
TC-013 | Account & Profile | "Personal Details" is active by default on first load | Automation — PASS
TC-014 | Account & Profile | "Personal Details" page heading is visible | Automation — PASS
TC-015 | Account & Profile | First name field is visible with value | Automation — PASS
TC-016 | Account & Profile | Last name field is visible with value | Automation — PASS
TC-017 | Account & Profile | Phone Number field is visible | Automation — PASS
TC-018 | Account & Profile | Email ID field is visible and masked | Automation — PASS
TC-019 | Account & Profile | Date of Birth section is visible with Year/Month/Date dropdowns | Automation — PASS
TC-020 | Account & Profile | Country dropdown is visible | Automation — PASS
TC-021 | Account & Profile | Pincode field is visible | Automation — PASS
TC-022 | Account & Profile | Save button is visible | Automation — PASS
TC-023 | Account & Profile | Fill Phone Number and Pincode then Save | Automation — PASS
TC-024 | Account & Profile | Saved values persist after page reload | Automation — PASS
TC-025 | Account & Profile | DOB Year dropdown can be changed | Automation — PASS
TC-026 | Account & Profile | Country dropdown can be changed | Automation — PASS
TC-027 | Account & Profile | "Organizational Details" page heading is visible | Automation — PASS
TC-028 | Account & Profile | "Background" label is visible | Automation — PASS
TC-029 | Account & Profile | Background dropdown shows current value (e.g. Healthcare Worker) | Automation — PASS
TC-030 | Account & Profile | Designation dropdown is visible (e.g. ANM/MPW) | Automation — PASS
TC-031 | Account & Profile | "RN/RM Number" label and field are visible | Automation — PASS
TC-032 | Account & Profile | Organization type / Private Sector dropdown is visible | Automation — PASS
TC-033 | Account & Profile | Organization Name input is visible | Automation — PASS
TC-034 | Account & Profile | Save button is visible on Organization Details | Automation — PASS
TC-035 | Account & Profile | Fill Organization Name and Save | Automation — PASS
TC-036 | Account & Profile | Saved Organization Name persists after reload | Automation — PASS
TC-037 | Account & Profile | "Education" heading is visible | Automation — PASS
TC-038 | Account & Profile | "+ Add Education" link is visible | Automation — PASS
TC-039 | Account & Profile | Clicking "+ Add Education" opens education entry form or modal | Automation — PASS
TC-040 | Account & Profile | "Academic Details" is highlighted as active in left nav | Automation — PASS
TC-041 | Account & Profile | "Language Preference" page heading is visible | Automation — PASS
TC-042 | Account & Profile | English radio option is visible | Automation — PASS
TC-043 | Account & Profile | Hindi radio option (हिंदी) is visible | Automation — PASS
TC-044 | Account & Profile | English is selected by default | Automation — PASS
TC-045 | Account & Profile | Save button is visible on Language Preference | Automation — PASS
TC-046 | Account & Profile | Select Hindi, click Save, verify Hindi remains selected after reload | Automation — PASS
TC-047 | Account & Profile | Switch back to English, save, verify English remains selected | Automation — PASS
TC-048 | Account & Profile | "My Certificates" is active in left nav | Automation — PASS
TC-049 | Account & Profile | Empty state "No Certificates" is visible for new users | Automation — PASS
TC-050 | Account & Profile | No certificate cards rendered when user has none | Automation — PASS
TC-051 | Account & Profile | Clicking the pencil icon opens an upload/edit option | Automation — PASS
TC-052 | Account & Profile | Clicking "Help and Support" navigates / opens helper | Automation — PASS
TC-053 | Account & Profile | Clicking Logout opens confirmation modal | Automation — PASS
TC-054 | Account & Profile | Logout modal shows "Are you sure?" text | Automation — PASS
TC-055 | Account & Profile | Logout modal has "Yes" and "No" buttons | Automation — PASS
TC-056 | Account & Profile | Clicking "No" in logout modal closes the modal and keeps user signed in | Automation — PASS
TC-057 | Account & Profile | Aastrika logo is visible on Account page | Automation — PASS
TC-058 | Account & Profile | Search bar is visible on Account page | Automation — PASS
TC-059 | Account & Profile | "Account" nav link is marked active | Automation — PASS
TC-060 | Account & Profile | Clicking "Home" navigates to Home page | Automation — PASS
TC-061 | Account & Profile | Dark mode toggle is visible on Account | Automation — PASS
TC-062 | Account & Profile | Notification bell is visible on Account | Automation — PASS
TC-063 | Account & Profile | No console errors on Account page load | Automation — PASS
TC-064 | Account & Profile | Page renders on mobile (390 × 844) | Automation — PASS
TC-065 | Account & Profile | Page renders on tablet (768 × 1024) | Automation — PASS
TC-066 | Account & Profile | Page renders on desktop (1440 × 900) | Automation — PASS
TC-067 | Account & Profile | URL persists on reload (page may need re-navigation via header) | Automation — PASS
TC-068 | Account & Profile | Unauthenticated access does not expose the profile | Automation — FAIL
TC-001 | Competency | Open Competency Dashboard | Automation — PASS
TC-002 | Competency | Required tab — detect if competencies load for this role | Automation — PASS
TC-003 | Competency | Role fix: open Account → Organizational Details | Automation — SKIP
TC-004 | Competency | Set Background = Healthcare Worker | Automation — SKIP
TC-005 | Competency | Set Designation = ANM/MPW | Automation — SKIP
TC-006 | Competency | Set Organization Type | Automation — SKIP
TC-007 | Competency | Save Organizational Details | Automation — SKIP
TC-008 | Competency | Reopen dashboard — competencies now available | Automation — PASS
TC-009 | Competency | Explore tab — Job Description (roles & competencies) | Automation — PASS
TC-010 | Competency | Explore tab — Passbook | Automation — PASS
TC-011 | Competency | Competencies are available (Required or Job Description) | Automation — PASS
TC-012 | Competency | Select target competency | Automation — PASS
TC-013 | Competency | Complete Level 1 | Automation — SKIP
TC-014 | Competency | Complete Level 2 | Automation — SKIP
TC-015 | Competency | Complete Level 3 | Automation — SKIP
TC-016 | Competency | Complete Level 4 | Automation — SKIP
TC-017 | Competency | Complete Level 5 | Automation — SKIP
TC-018 | Competency | Complete Level 6 | Automation — SKIP
TC-019 | Competency | Complete Level 7 | Automation — SKIP
TC-020 | Competency | Complete Level 8 | Automation — SKIP
TC-021 | Competency | Complete Level 9 | Automation — SKIP
TC-022 | Competency | Complete Level 10 | Automation — SKIP
TC-023 | Competency | Passbook displays the completed assessment(s) | Automation — PASS
TC-001 | My Courses | Page heading "My Courses" is visible | Automation — PASS
TC-002 | My Courses | URL contains "/my_courses" | Automation — PASS
TC-003 | My Courses | "Started" tab is visible with count | Automation — PASS
TC-004 | My Courses | "For You" tab is visible with count | Automation — PASS
TC-005 | My Courses | "Completed" tab is visible with count | Automation — PASS
TC-006 | My Courses | "Started" tab is active by default | Automation — PASS
TC-007 | My Courses | Tab count totals are non-negative integers | Automation — PASS
TC-008 | My Courses | Started tab content is displayed when active | Automation — PASS
TC-009 | My Courses | First Started course displays a thumbnail image | Automation — PASS
TC-010 | My Courses | First Started course displays a title | Automation — PASS
TC-011 | My Courses | Progress bar is visible on Started courses | Automation — PASS
TC-012 | My Courses | Progress percentage is displayed (e.g. "0% Complete" or "11% Complete") | Automation — PASS
TC-013 | My Courses | "Resume" button is visible on each Started course | Automation — PASS
TC-014 | My Courses | Clicking "Resume" navigates to the course player | Automation — PASS
TC-015 | My Courses | Clicking a course title navigates to the course | Automation — PASS
TC-016 | My Courses | Started tab count matches actual course rows visible | Automation — PASS
TC-017 | My Courses | For You tab content is displayed when active | Automation — PASS
TC-018 | My Courses | For You section displays course cards in a grid | Automation — PASS
TC-019 | My Courses | Course thumbnail is visible on each For You card | Automation — PASS
TC-020 | My Courses | "Certificate" badge is visible on cards (top-left) | Automation — PASS
TC-021 | My Courses | Star rating with number (e.g. 4.7 ⭐) is visible on cards | Automation — PASS
TC-022 | My Courses | Provider tag is visible on cards (e.g. Indian Nursing Council, Jhpiego) | Automation — PASS
TC-023 | My Courses | Course titles are visible on For You cards | Automation — PASS
TC-024 | My Courses | Clicking a For You card opens the course detail page | Automation — PASS
TC-025 | My Courses | For You tab count matches displayed card count | Automation — PASS
TC-026 | My Courses | For You cards are arranged in 3-column grid on desktop | Automation — PASS
TC-027 | My Courses | Completed tab becomes active when clicked | Automation — PASS
TC-028 | My Courses | Completed tab count is 0 for new user | Automation — PASS
TC-029 | My Courses | Empty-state message is visible when no courses completed | Automation — PASS
TC-030 | My Courses | Empty-state message text matches exactly | Automation — PASS
TC-031 | My Courses | No course cards are visible when Completed tab is empty | Automation — PASS
TC-032 | My Courses | No "Resume" buttons appear in Completed tab | Automation — PASS
TC-033 | My Courses | Started → For You switch shows different content | Automation — PASS
TC-034 | My Courses | For You → Completed switch shows empty state | Automation — PASS
TC-035 | My Courses | Completed → Started restores Started content | Automation — PASS
TC-036 | My Courses | Each tab switch keeps URL on /my_courses | Automation — FAIL
TC-001 | Course Table of Contents | TOC: course title is visible | Automation — PASS
TC-002 | Course Table of Contents | TOC: "CNE hours" badge is visible | Automation — PASS
TC-003 | Course Table of Contents | TOC: course duration is visible | Automation — PASS
TC-004 | Course Table of Contents | TOC: rating and review count are visible | Automation — PASS
TC-005 | Course Table of Contents | TOC: author "By: <organization>" is visible | Automation — PASS
TC-006 | Course Table of Contents | TOC: Details / Certificate / Share icons are visible | Automation — PASS
TC-007 | Course Table of Contents | TOC: "Details" opens the details popup | Automation — PASS
TC-008 | Course Table of Contents | TOC: "X" closes the details popup | Automation — PASS
TC-009 | Course Table of Contents | TOC: "Certificate" shows a popup | Automation — PASS
TC-010 | Course Table of Contents | TOC: "Close" closes the certificate popup | Automation — PASS
TC-011 | Course Table of Contents | TOC: "Share" shows shareable options | Automation — PASS
TC-012 | Course Table of Contents | TOC: Resume/Start button is visible | Automation — FAIL
TC-013 | Course Table of Contents | TOC: Overview / Modules / Discussion tabs are visible | Automation — PASS
TC-014 | Course Table of Contents | TOC: "Modules" tab opens the module list | Automation — PASS
TC-015 | Course Table of Contents | TOC: "Discussion" tab is clickable | Automation — PASS
TC-016 | Course Table of Contents | TOC: "Description" section is visible | Automation — PASS
TC-017 | Course Table of Contents | TOC: "License terms" section is visible | Automation — PASS
TC-018 | Course Table of Contents | TOC: License terms shows the Creative Commons link | Automation — PASS
TC-019 | Course Table of Contents | TOC: clicking the author opens the organization page | Automation — PASS
TC-020 | Course Table of Contents | TOC: back icon leaves the course overview | Automation — SKIP
TC-021 | Course Table of Contents | TOC: "Start"/"Resume" opens the course player | Automation — PASS
TC-001 | Course Completion | Complete course end-to-end | Automation — PASS
TC-001 | Public Pages | Aastrika Sphere logo is visible | Automation — PASS
TC-002 | Public Pages | Log in button is visible and clickable - closes modal after | Automation — PASS
TC-003 | Public Pages | "Access free Healthcare courses" heading is visible | Automation — PASS
TC-004 | Public Pages | "Learn at your own pace & Get Certified" subtext is visible | Automation — PASS
TC-005 | Public Pages | "New User?" text is visible | Automation — PASS
TC-006 | Public Pages | Create Account button is visible and clickable | Automation — PASS
TC-007 | Public Pages | CNE Hours banner - "Check out courses with CNE Hours" is visible | Automation — PASS
TC-008 | Public Pages | CNE Hours banner - "View courses" button is clickable | Automation — PASS
TC-009 | Public Pages | Banner carousel dots are visible and clickable | Automation — PASS
TC-010 | Public Pages | "310,000+ Learners onboarded" stat is visible | Automation — PASS
TC-011 | Public Pages | "490+ Number of courses" stat is visible | Automation — PASS
TC-012 | Public Pages | "57.5 CNE Hours" stat is visible | Automation — PASS
TC-013 | Public Pages | "400,000+ Total certificate issued" stat is visible | Automation — PASS
TC-014 | Public Pages | "TOP COURSES" heading is visible | Automation — PASS
TC-015 | Public Pages | "View All" link in Top Courses is visible and clickable | Automation — PASS
TC-016 | Public Pages | Top course cards are visible | Automation — PASS
TC-017 | Public Pages | Top course cards show Certificate badge | Automation — PASS
TC-018 | Public Pages | Top course cards show star ratings | Automation — PASS
TC-019 | Public Pages | First top course card is clickable | Automation — PASS
TC-020 | Public Pages | "CNE COURSES" heading is visible | Automation — PASS
TC-021 | Public Pages | "View All" link in CNE Courses is clickable | Automation — PASS
TC-022 | Public Pages | CNE course cards are visible | Automation — PASS
TC-023 | Public Pages | CNE course cards show CNE hours badge | Automation — PASS
TC-024 | Public Pages | CNE section carousel right arrow is clickable | Automation — PASS
TC-025 | Public Pages | First CNE course card is clickable - "Normal Labour & Birth and AMTSL" | Automation — PASS
TC-026 | Public Pages | Second CNE course card is clickable - "Integrated Sexual and Reproductive Health" | Automation — PASS
TC-027 | Public Pages | Partner logos - Indian Nursing Council badge visible | Automation — PASS
TC-028 | Public Pages | Partner logos - UNFPA badge visible | Automation — PASS
TC-029 | Public Pages | "Trusted By" heading is visible | Automation — PASS
TC-030 | Public Pages | "50+ Partner Organizations and Growing" is visible | Automation — PASS
TC-031 | Public Pages | Fernandez Foundation logo is visible | Automation — PASS
TC-032 | Public Pages | Manyata logo is visible | Automation — PASS
TC-033 | Public Pages | KLE logo is visible | Automation — PASS
TC-034 | Public Pages | UNFPA logo is visible | Automation — PASS
TC-035 | Public Pages | NQOCN logo is visible | Automation — PASS
TC-036 | Public Pages | "How Sphere works" heading is visible | Automation — PASS
TC-037 | Public Pages | "In 3-simple videos" subtitle is visible | Automation — PASS
TC-038 | Public Pages | Step 1 - "Register for a course" card is visible and play button works | Automation — PASS
TC-039 | Public Pages | Step 2 - "Take the course" card is visible and play button works | Automation — PASS
TC-040 | Public Pages | Step 3 - "Get certified" card is visible and play button works | Automation — PASS
TC-041 | Public Pages | "Transform your Healthcare career through Sphere!" text is visible | Automation — PASS
TC-042 | Public Pages | "Start Today" button is visible and clickable | Automation — PASS
TC-043 | Public Pages | "An initiative of" section is visible | Automation — PASS
TC-044 | Public Pages | Nilekani Philanthropies logo is visible | Automation — PASS
TC-045 | Public Pages | "A collaboration with" section is visible | Automation — PASS
TC-046 | Public Pages | Societal Platform logo is visible | Automation — PASS
TC-047 | Public Pages | "Quick Links" heading in footer is visible | Automation — PASS
TC-048 | Public Pages | "Privacy policy" link is visible and clickable | Automation — PASS
TC-049 | Public Pages | "Terms of Use" link is visible and clickable | Automation — PASS
TC-050 | Public Pages | "Help & Contact" heading in footer is visible | Automation — PASS
TC-051 | Public Pages | "support@aastrika.org" email link is visible | Automation — PASS
TC-052 | Public Pages | "Talk to us on WhatsApp" button is visible and clickable | Automation — PASS
TC-053 | Public Pages | "Additional Links" heading is visible | Automation — PASS
TC-054 | Public Pages | "Aastrika Foundation" link is visible and has correct href | Automation — PASS
TC-055 | Public Pages | Twitter/X social icon is visible and clickable | Automation — PASS
TC-056 | Public Pages | Facebook social icon is visible and clickable | Automation — PASS
TC-057 | Public Pages | Instagram social icon is visible and clickable | Automation — PASS
TC-058 | Public Pages | LinkedIn social icon is visible and clickable | Automation — PASS
TC-059 | Public Pages | Copyright text is visible | Automation — PASS
TC-060 | Public Pages | Aastrika Sphere footer logo is visible | Automation — PASS
TC-061 | Public Pages | No broken images on the entire public page | Automation — FAIL
TC-062 | Public Pages | No console errors on page load | Automation — PASS
TC-063 | Public Pages | Page loads within 10 seconds | Automation — PASS
TC-064 | Public Pages | Page title contains Sphere or Aastrika | Automation — PASS
TC-001 | Private Pages | Aastrika Sphere logo is visible | Automation — PASS
TC-002 | Private Pages | Logo click navigates to Home | Automation — PASS
TC-003 | Private Pages | Search bar is visible and accepts input | Automation — PASS
TC-004 | Private Pages | Search submission triggers search | Automation — PASS
TC-005 | Private Pages | Search icon is visible | Automation — PASS
TC-006 | Private Pages | Dark mode toggle is visible | Automation — PASS
TC-007 | Private Pages | Dark mode toggle changes theme | Automation — PASS
TC-008 | Private Pages | "Home" nav link is visible | Automation — PASS
TC-009 | Private Pages | "My Courses" nav link is visible and clickable | Automation — PASS
TC-010 | Private Pages | "Competency" nav link is visible and clickable | Automation — PASS
TC-011 | Private Pages | "Account" nav link is visible and clickable | Automation — PASS
TC-012 | Private Pages | Notification bell icon is visible | Automation — PASS
TC-013 | Private Pages | Notification bell click opens panel/popup | Automation — PASS
TC-014 | Private Pages | "Welcome !" greeting is visible | Automation — PASS
TC-015 | Private Pages | User's display name is shown | Automation — PASS
TC-016 | Private Pages | "Start Learning" subtitle is visible | Automation — PASS
TC-017 | Private Pages | Hero carousel banner is visible | Automation — PASS
TC-018 | Private Pages | "Watch how Sphere works" text is visible | Automation — PASS
TC-019 | Private Pages | "Watch now" button is visible and clickable | Automation — PASS
TC-020 | Private Pages | Carousel pagination dots are visible | Automation — PASS
TC-021 | Private Pages | Clicking carousel dot switches slide | Automation — PASS
TC-022 | Private Pages | "CONTINUE LEARNING" section heading is visible | Automation — PASS
TC-023 | Private Pages | "View All" link visible for Continue Learning | Automation — PASS
TC-024 | Private Pages | Continue Learning course cards are clickable | Automation — PASS
TC-025 | Private Pages | "CNE COURSES" section heading is visible | Automation — PASS
TC-026 | Private Pages | "View All" link visible for CNE Courses | Automation — FAIL
TC-027 | Private Pages | CNE Courses section has cards | Automation — PASS
TC-028 | Private Pages | First CNE card shows course title | Automation — PASS
TC-029 | Private Pages | CNE points badge is visible on cards | Automation — PASS
TC-030 | Private Pages | Course rating (e.g. 4.7) is visible on cards | Automation — PASS
TC-031 | Private Pages | Provider tag is visible | Automation — PASS
TC-032 | Private Pages | First CNE card click navigates to course detail | Automation — PASS
TC-033 | Private Pages | "View All" CNE click navigates | Automation — PASS
TC-034 | Private Pages | CNE Courses horizontal scroll arrows | Automation — PASS
TC-035 | Private Pages | "Register for a course" card is visible | Automation — PASS
TC-036 | Private Pages | "Register for a course" subtitle is visible | Automation — PASS
TC-037 | Private Pages | "Take the course" card is visible | Automation — PASS
TC-038 | Private Pages | "Take the course" subtitle is visible | Automation — PASS
TC-039 | Private Pages | "Get certified" card is visible | Automation — PASS
TC-040 | Private Pages | "Get certified" subtitle is visible | Automation — PASS
TC-041 | Private Pages | Register card click behavior | Automation — PASS
TC-042 | Private Pages | Take card click behavior | Automation — PASS
TC-043 | Private Pages | Get certified card click behavior | Automation — PASS
TC-044 | Private Pages | Footer Aastrika Sphere logo is visible | Automation — PASS
TC-045 | Private Pages | "Quick Links" heading is visible | Automation — PASS
TC-046 | Private Pages | "Privacy policy" link is visible and clickable | Automation — PASS
TC-047 | Private Pages | "Terms of Use" link is visible and clickable | Automation — PASS
TC-048 | Private Pages | "Help & Contact" heading is visible | Automation — PASS
TC-049 | Private Pages | Support email link is visible | Automation — PASS
TC-050 | Private Pages | "Talk to us on WhatsApp" button is visible | Automation — PASS
TC-051 | Private Pages | WhatsApp button click opens WhatsApp | Automation — PASS
TC-052 | Private Pages | "Additional Links" heading is visible | Automation — PASS
TC-053 | Private Pages | "Aastrika Foundation" link is visible with URL | Automation — PASS
TC-054 | Private Pages | Aastrika Foundation link opens in new tab | Automation — PASS
TC-055 | Private Pages | Twitter social icon is visible | Automation — PASS
TC-056 | Private Pages | Facebook social icon is visible | Automation — PASS
TC-057 | Private Pages | Instagram social icon is visible | Automation — PASS
TC-058 | Private Pages | LinkedIn social icon is visible | Automation — PASS
TC-059 | Private Pages | Copyright notice is visible | Automation — PASS
TC-060 | Private Pages | Copyright year is current | Automation — PASS
TC-061 | Private Pages | Page title contains "Aastrika" or "Sphere" | Automation — PASS
TC-062 | Private Pages | No console errors on page load | Automation — PASS
TC-063 | Private Pages | Page renders on mobile viewport (390 × 844) | Automation — PASS
TC-064 | Private Pages | Page renders on tablet viewport (768 × 1024) | Automation — PASS
TC-065 | Private Pages | Page renders on desktop viewport (1440 × 900) | Automation — PASS
TC-066 | Private Pages | Header stays sticky on scroll | Automation — PASS
TC-067 | Private Pages | Footer is visible after scroll | Automation — PASS

## Manual — Master Coverage
Learner Portal — Manual Master Test Suite (Coverage)
628 documented manual test cases across 11 modules · status shown as recorded in the master suite
Test Case ID | Modules | Test Case Description | Status (Manual / Automation)
TC-0001 | Public Page | Verify Aastrika Sphere logo is visible | Manual — PASS
TC-0002 | Public Page | Verify Log In button is visible in header | Manual — PASS
TC-0003 | Public Page | Verify Log In button is clickable and opens login modal | Manual — PASS
TC-0004 | Public Page | Verify login modal can be closed | Manual — PASS
TC-0005 | Public Page | Verify 'Access free Healthcare courses' heading is visible | Manual — PASS
TC-0006 | Public Page | Verify 'Learn at your own pace & Get Certified' subtext is visible | Manual — PASS
TC-0007 | Public Page | Verify 'New User?' label is visible | Manual — PASS
TC-0008 | Public Page | Verify Create Account button is visible and enabled | Manual — PASS
TC-0009 | Public Page | Verify Create Account button navigates to registration page | Manual — PASS
TC-0010 | Public Page | Verify CNE Hours banner text is visible | Manual — PASS
TC-0011 | Public Page | Verify 'View courses' button in CNE banner is clickable | Manual — PASS
TC-0012 | Public Page | Verify carousel dot 1 (active) is visible | Manual — PASS
TC-0013 | Public Page | Verify carousel dot 2 is clickable and changes slide | Manual — PASS
TC-0014 | Public Page | Verify carousel auto-rotates or responds to dot click | Manual — PASS
TC-0015 | Public Page | Verify '310,000+ Learners onboarded' stat is visible | Manual — PASS
TC-0016 | Public Page | Verify '490+ Number of courses' stat is visible | Manual — PASS
TC-0017 | Public Page | Verify '57.5 CNE Hours' stat is visible | Manual — PASS
TC-0018 | Public Page | Verify '400,000+ Total certificate issued' stat is visible | Manual — PASS
TC-0019 | Public Page | Verify all 4 stat cards are visible simultaneously | Manual — PASS
TC-0020 | Public Page | Verify 'TOP COURSES' section heading is visible | Manual — PASS
TC-0021 | Public Page | Verify 'View All' link in Top Courses is visible | Manual — PASS
TC-0022 | Public Page | Verify 'View All' in Top Courses is clickable | Manual — PASS
TC-0023 | Public Page | Verify top course cards are displayed | Manual — PASS
TC-0024 | Public Page | Verify each course card shows 'Certificate' badge | Manual — PASS
TC-0025 | Public Page | Verify each course card shows star rating | Manual — PASS
TC-0026 | Public Page | Verify clicking a course card navigates to course detail page | Manual — PASS
TC-0027 | Public Page | Verify course card thumbnail image loads correctly | Manual — PASS
TC-0028 | Public Page | Verify 'CNE COURSES' section heading is visible | Manual — PASS
TC-0029 | Public Page | Verify 'View All' link in CNE Courses is visible and clickable | Manual — PASS
TC-0030 | Public Page | Verify CNE course cards are displayed | Manual — PASS
TC-0031 | Public Page | Verify CNE badge is shown on each card (e.g., CNE: 7.5) | Manual — PASS
TC-0032 | Public Page | Verify star rating is shown on each CNE course card | Manual — PASS
TC-0033 | Public Page | Verify organisation badge shown on card (e.g., Indian Nursing Council) | Manual — PASS
TC-0034 | Public Page | Verify 'Normal Labour & Birth and AMTSL' card is visible and clickable | Manual — PASS
TC-0035 | Public Page | Verify 'Integrated Sexual and Reproductive Health (ISRH)' card is visible and clickable | Manual — PASS
TC-0036 | Public Page | Verify Hindi course cards are displayed | Manual — PASS
TC-0037 | Public Page | Verify carousel right-arrow button is visible and clickable | Manual — PASS
TC-0038 | Public Page | Verify 'Trusted By' heading is visible | Manual — PASS
TC-0039 | Public Page | Verify '50+ Partner Organizations and Growing' subtext is visible | Manual — PASS
TC-0040 | Public Page | Verify Fernandez Foundation logo is visible | Manual — PASS
TC-0041 | Public Page | Verify Manyata logo is visible | Manual — PASS
TC-0042 | Public Page | Verify KLE Academy of Higher Education logo is visible | Manual — PASS
TC-0043 | Public Page | Verify UNFPA logo is visible in partner section | Manual — PASS
TC-0044 | Public Page | Verify NQOCN logo is visible | Manual — PASS
TC-0045 | Public Page | Verify The White Ribbon Alliance logo is visible | Manual — PASS
TC-0046 | Public Page | Verify 'How Sphere works' heading is visible | Manual — PASS
TC-0047 | Public Page | Verify subtitle 'In 3-simple videos…' is visible | Manual — PASS
TC-0048 | Public Page | Verify Step 1 — 'Register for a course' card is visible | Manual — PASS
TC-0049 | Public Page | Verify Step 1 play button is clickable | Manual — PASS
TC-0050 | Public Page | Verify Step 2 — 'Take the course' card is visible | Manual — PASS
TC-0051 | Public Page | Verify Step 2 play button is clickable | Manual — PASS
TC-0052 | Public Page | Verify Step 3 — 'Get certified' card is visible | Manual — PASS
TC-0053 | Public Page | Verify Step 3 play button is clickable | Manual — PASS
TC-0054 | Public Page | Verify 'Transform your Healthcare career through Sphere!' text is visible | Manual — PASS
TC-0055 | Public Page | Verify 'Start Today' button is visible | Manual — PASS
TC-0056 | Public Page | Verify 'Start Today' button is enabled | Manual — PASS
TC-0057 | Public Page | Verify 'Start Today' button navigates to Create Account page | Manual — PASS
TC-0058 | Public Page | Verify 'An initiative of' label is visible | Manual — PASS
TC-0059 | Public Page | Verify Nilekani Philanthropies logo is visible | Manual — PASS
TC-0060 | Public Page | Verify 'A collaboration with' label is visible | Manual — PASS
TC-0061 | Public Page | Verify Societal Platform logo is visible | Manual — PASS
TC-0062 | Public Page | Verify Aastrika Sphere logo in footer is visible | Manual — PASS
TC-0063 | Public Page | Verify 'Quick Links' heading in footer is visible | Manual — PASS
TC-0064 | Public Page | Verify 'Privacy policy' link is visible in footer | Manual — PASS
TC-0065 | Public Page | Verify 'Privacy policy' link is clickable and navigates to policy page | Manual — PASS
TC-0066 | Public Page | Verify 'Terms of Use' link is visible in footer | Manual — PASS
TC-0067 | Public Page | Verify 'Terms of Use' link is clickable and navigates to terms page | Manual — PASS
TC-0068 | Public Page | Verify 'Help & Contact' heading is visible in footer | Manual — PASS
TC-0069 | Public Page | Verify 'support@aastrika.org' email link is visible | Manual — PASS
TC-0070 | Public Page | Verify support email has correct mailto href | Manual — PASS
TC-0071 | Public Page | Verify 'Talk to us on WhatsApp' button is visible | Manual — PASS
TC-0072 | Public Page | Verify 'Talk to us on WhatsApp' button has valid WhatsApp link | Manual — PASS
TC-0073 | Public Page | Verify 'Additional Links' heading is visible | Manual — PASS
TC-0074 | Public Page | Verify 'Aastrika Foundation: https://www.aastrika.org/' link is visible | Manual — PASS
TC-0075 | Public Page | Verify Aastrika Foundation link is clickable and opens correct URL | Manual — PASS
TC-0076 | Public Page | Verify Twitter/X social icon is visible in footer | Manual — PASS
TC-0077 | Public Page | Verify Twitter/X icon has valid href and is clickable | Manual — PASS
TC-0078 | Public Page | Verify Facebook social icon is visible in footer | Manual — PASS
TC-0079 | Public Page | Verify Facebook icon has valid href and is clickable | Manual — PASS
TC-0080 | Public Page | Verify Instagram social icon is visible in footer | Manual — PASS
TC-0081 | Public Page | Verify Instagram icon has valid href and is clickable | Manual — PASS
TC-0082 | Public Page | Verify LinkedIn social icon is visible in footer | Manual — PASS
TC-0083 | Public Page | Verify LinkedIn icon has valid href and is clickable | Manual — PASS
TC-0084 | Public Page | Verify copyright text is visible | Manual — PASS
TC-0085 | Public Page | Verify no broken images exist on the full public page | Manual — PASS
TC-0086 | Public Page | Verify no console errors on page load | Manual — PASS
TC-0087 | Public Page | Verify page load time is under 10 seconds | Manual — PASS
TC-0088 | Public Page | Verify page title contains 'Sphere' or 'Aastrika' | Manual — PASS
TC-0089 | Public Page | Verify page URL is correct | Manual — PASS
TC-0090 | Public Page | Verify page is responsive at 1280x720 desktop viewport | Manual — PASS
TC-0091 | My Courses | Verify "My Courses" page heading is visible | Manual — PASS
TC-0092 | My Courses | Verify URL contains "/my_courses" | Manual — PASS
TC-0093 | My Courses | Verify "Started" tab is visible with course count | Manual — PASS
TC-0094 | My Courses | Verify "For You" tab is visible with course count | Manual — PASS
TC-0095 | My Courses | Verify "Completed" tab is visible with course count | Manual — PASS
TC-0096 | My Courses | Verify "Started" tab is selected by default | Manual — PASS
TC-0097 | My Courses | Verify all tab counts are non-negative integers | Manual — PASS
TC-0098 | My Courses | Verify Started tab content is displayed when tab is active | Manual — PASS
TC-0099 | My Courses | Verify each Started course displays a thumbnail image | Manual — PASS
TC-0100 | My Courses | Verify each Started course displays its title | Manual — PASS
TC-0101 | My Courses | Verify progress bar is visible on each Started course | Manual — PASS
TC-0102 | My Courses | Verify progress percentage text is displayed | Manual — PASS
TC-0103 | My Courses | Verify "Resume" button is visible on each Started course | Manual — PASS
TC-0104 | My Courses | Verify clicking "Resume" navigates to the course player | Manual — PASS
TC-0105 | My Courses | Verify clicking the course title navigates to the course | Manual — PASS
TC-0106 | My Courses | Verify Started tab count matches the actual number of visible course rows | Manual — PASS
TC-0107 | My Courses | Verify For You tab content is displayed when tab is active | Manual — PASS
TC-0108 | My Courses | Verify For You section displays course cards in a grid layout | Manual — PASS
TC-0109 | My Courses | Verify each For You card displays a thumbnail image | Manual — PASS
TC-0110 | My Courses | Verify "Certificate" badge is visible on each card (top-left) | Manual — PASS
TC-0111 | My Courses | Verify star rating is visible on each card (top-right) | Manual — PASS
TC-0112 | My Courses | Verify provider tag is visible on each card | Manual — PASS
TC-0113 | My Courses | Verify course titles are visible on each card | Manual — PASS
TC-0114 | My Courses | Verify clicking a For You card opens the course detail page | Manual — PASS
TC-0115 | My Courses | Verify For You tab count matches displayed card count | Manual — PASS
TC-0116 | My Courses | Verify For You grid is responsive on smaller viewports | Manual — PASS
TC-0117 | My Courses | Verify Completed tab becomes active when clicked | Manual — PASS
TC-0118 | My Courses | Verify Completed tab count is 0 for a new user | Manual — PASS
TC-0119 | My Courses | Verify empty-state message is visible when no courses are completed | Manual — PASS
TC-0120 | My Courses | Verify empty-state message exact text matches | Manual — PASS
TC-0121 | My Courses | Verify no course cards are visible when Completed tab is empty | Manual — PASS
TC-0122 | My Courses | Verify no "Resume" buttons appear in the Completed tab | Manual — PASS
TC-0123 | My Courses | Verify Started → For You switch displays different content | Manual — PASS
TC-0124 | My Courses | Verify For You → Completed switch shows empty state | Manual — PASS
TC-0125 | My Courses | Verify Completed → Started switch restores Started content | Manual — PASS
TC-0126 | My Courses | Verify URL stays on /my_courses across all tab switches | Manual — PASS
TC-0127 | My Courses | Verify Aastrika Sphere logo is visible on My Courses | Manual — PASS
TC-0128 | My Courses | Verify search bar is visible on My Courses | Manual — PASS
TC-0129 | My Courses | Verify "My Courses" nav link is marked as active | Manual — PASS
TC-0130 | My Courses | Verify clicking "Home" from My Courses navigates to Home page | Manual — PASS
TC-0131 | My Courses | Verify dark mode toggle is visible on My Courses | Manual — PASS
TC-0132 | My Courses | Verify notification bell is visible on My Courses | Manual — PASS
TC-0133 | My Courses | Verify My Courses loads without console errors | Manual — PASS
TC-0134 | My Courses | Verify My Courses renders correctly on mobile viewport (390 × 844) | Manual — PASS
TC-0135 | My Courses | Verify My Courses renders correctly on tablet viewport (768 × 1024) | Manual — PASS
TC-0136 | My Courses | Verify My Courses renders correctly on desktop viewport (1440 × 900) | Manual — PASS
TC-0137 | My Courses | Verify browser tab title contains "Aastrika", "Sphere", or "Courses" | Manual — PASS
TC-0138 | My Courses | Verify URL persists on page reload | Manual — PASS
TC-0139 | My Courses | Verify unauthenticated access to My Courses redirects to login | Manual — PASS
TC-0140 | Account | Verify URL contains "/profile" (or account path) | Manual — PASS
TC-0141 | Account | Verify user name is visible in left panel | Manual — PASS
TC-0142 | Account | Verify position label is visible | Manual — PASS
TC-0143 | Account | Verify profile avatar image is visible | Manual — PASS
TC-0144 | Account | Verify pencil edit icon on profile picture is visible | Manual — PASS
TC-0145 | Account | Verify "Personal Details" nav link is visible | Manual — PASS
TC-0146 | Account | Verify "Organization Details" nav link is visible | Manual — PASS
TC-0147 | Account | Verify "Academic Details" nav link is visible | Manual — PASS
TC-0148 | Account | Verify "Language Preference" nav link is visible | Manual — PASS
TC-0149 | Account | Verify "My Certificates" nav link is visible | Manual — PASS
TC-0150 | Account | Verify "Help and Support" button is visible | Manual — PASS
TC-0151 | Account | Verify "Logout" button is visible | Manual — PASS
TC-0152 | Account | Verify "Personal Details" is active by default on first load | Manual — PASS
TC-0153 | Account | Verify "Personal Details" page heading is visible | Manual — PASS
TC-0154 | Account | Verify First Name field is visible with value | Manual — PASS
TC-0155 | Account | Verify Last Name field is visible with value | Manual — PASS
TC-0156 | Account | Verify Phone Number field is visible | Manual — PASS
TC-0157 | Account | Verify Email ID field is visible and masked | Manual — PASS
TC-0158 | Account | Verify Date of Birth section is visible with Year/Month/Date dropdowns | Manual — PASS
TC-0159 | Account | Verify Country dropdown is visible | Manual — PASS
TC-0160 | Account | Verify Pincode field is visible | Manual — PASS
TC-0161 | Account | Verify Save button is visible | Manual — PASS
TC-0162 | Account | Verify Fill Phone Number and Pincode then Save works | Manual — PASS
TC-0163 | Account | Verify saved values persist after page reload | Manual — PASS
TC-0164 | Account | Verify DOB Year dropdown can be changed | Manual — PASS
TC-0165 | Account | Verify Country dropdown can be changed | Manual — PASS
TC-0166 | Account | Verify "Organizational Details" page heading is visible | Manual — PASS
TC-0167 | Account | Verify "Background" label is visible | Manual — PASS
TC-0168 | Account | Verify Background dropdown shows current value | Manual — PASS
TC-0169 | Account | Verify Designation dropdown is visible | Manual — PASS
TC-0170 | Account | Verify "RN/RM Number" label and field are visible | Manual — PASS
TC-0171 | Account | Verify Organization type / Private Sector dropdown is visible | Manual — PASS
TC-0172 | Account | Verify Organization Name input is visible | Manual — PASS
TC-0173 | Account | Verify Save button is visible on Organization Details | Manual — PASS
TC-0174 | Account | Verify Fill Organization Name and Save works | Manual — PASS
TC-0175 | Account | Verify saved Organization Name persists after reload | Manual — PASS
TC-0176 | Account | Verify "Education" heading is visible | Manual — PASS
TC-0177 | Account | Verify "+ Add Education" link is visible | Manual — PASS
TC-0178 | Account | Verify clicking "+ Add Education" opens entry form or modal | Manual — PASS
TC-0179 | Account | Verify "Academic Details" is highlighted as active in left nav | Manual — PASS
TC-0180 | Account | Verify "Language Preference" page heading is visible | Manual — PASS
TC-0181 | Account | Verify English radio option is visible | Manual — PASS
TC-0182 | Account | Verify Hindi radio option (हिंदी) is visible | Manual — PASS
TC-0183 | Account | Verify English is selected by default | Manual — PASS
TC-0184 | Account | Verify Save button is visible on Language Preference | Manual — PASS
TC-0185 | Account | Verify Select Hindi, Save, and persistence after reload | Manual — PASS
TC-0186 | Account | Verify Switch back to English, Save, and persistence | Manual — PASS
TC-0187 | Account | Verify "My Certificates" is active in left nav | Manual — PASS
TC-0188 | Account | Verify empty state "No Certificates" is visible for new users | Manual — PASS
TC-0189 | Account | Verify no certificate cards are rendered when user has none | Manual — PASS
TC-0190 | Account | Verify clicking the pencil icon opens an upload/edit option | Manual — PASS
TC-0191 | Account | Verify clicking "Help and Support" navigates or opens helper | Manual — PASS
TC-0192 | Account | Verify clicking Logout opens confirmation modal | Manual — PASS
TC-0193 | Account | Verify Logout modal shows "Are you sure?" text | Manual — PASS
TC-0194 | Account | Verify Logout modal has "Yes" and "No" buttons | Manual — PASS
TC-0195 | Account | Verify clicking "No" closes modal and keeps user signed in | Manual — PASS
TC-0196 | Account | Verify Aastrika logo is visible on Account page | Manual — PASS
TC-0197 | Account | Verify search bar is visible on Account page | Manual — PASS
TC-0198 | Account | Verify "Account" nav link is marked active | Manual — PASS
TC-0199 | Account | Verify clicking "Home" navigates to Home page | Manual — PASS
TC-0200 | Account | Verify dark mode toggle is visible on Account | Manual — PASS
TC-0201 | Account | Verify notification bell is visible on Account | Manual — PASS
TC-0202 | Account | Verify no console errors on Account page load | Manual — PASS
TC-0203 | Account | Verify page renders on mobile (390 × 844) | Manual — PASS
TC-0204 | Account | Verify page renders on tablet (768 × 1024) | Manual — PASS
TC-0205 | Account | Verify page renders on desktop (1440 × 900) | Manual — PASS
TC-0206 | Account | Verify URL persists on reload | Manual — PASS
TC-0207 | Account | Verify unauthenticated access redirects to login | Manual — PASS
TC-0208 | Create Account | Verify Aastrika Sphere logo is visible on language page | Manual — PASS
TC-0209 | Create Account | Verify "Select Language" heading is visible | Manual — PASS
TC-0210 | Create Account | Verify no language is pre-selected on first page load | Manual — PASS
TC-0211 | Create Account | Verify Next button is disabled until a language is selected | Manual — PASS
TC-0212 | Create Account | Verify English radio is visible and selectable via radio button click | Manual — PASS
TC-0213 | Create Account | Verify English can be selected by clicking the "English" text label | Manual — PASS
TC-0214 | Create Account | Verify Hindi (हिंदी) radio option is visible and selectable | Manual — PASS
TC-0215 | Create Account | Verify selecting Hindi unselects English (single-choice behavior) | Manual — PASS
TC-0216 | Create Account | Verify switching back from Hindi to English works | Manual — PASS
TC-0217 | Create Account | Verify Next button enables after a language is selected | Manual — PASS
TC-0218 | Create Account | Verify Next button navigates to Create Your Account form after selecting English | Manual — PASS
TC-0219 | Create Account | Verify Next button works when Hindi is selected | Manual — PASS
TC-0220 | Create Account | Verify "Create your account" heading is visible | Manual — PASS
TC-0221 | Create Account | Verify "Start by entering your details" sub-heading is visible | Manual — PASS
TC-0222 | Create Account | Verify First Name field is visible and accepts input | Manual — PASS
TC-0223 | Create Account | Verify Last Name field is visible and accepts input | Manual — PASS
TC-0224 | Create Account | Verify Phone/Email field accepts a valid email address | Manual — PASS
TC-0225 | Create Account | Verify Phone/Email field accepts a valid phone number | Manual — PASS
TC-0226 | Create Account | Verify "Choose your Login method" heading is visible | Manual — PASS
TC-0227 | Create Account | "By OTP" radio option is visible and selectable | Manual — PASS
TC-0228 | Create Account | "By password" radio option is visible and selectable | Manual — PASS
TC-0229 | Create Account | Verify selecting one login method unselects the other | Manual — PASS
TC-0230 | Create Account | Verify Next button is disabled when required fields are empty | Manual — PASS
TC-0231 | Create Account | Verify Next button enables with all required fields filled | Manual — PASS
TC-0232 | Create Account | Verify Next button click opens Name Confirmation modal | Manual — PASS
TC-0233 | Create Account | Verify First Name handles empty input | Manual — PASS
TC-0234 | Create Account | Verify First Name handles single character | Manual — PASS
TC-0235 | Create Account | Verify First Name handles hyphenated name | Manual — PASS
TC-0236 | Create Account | Verify First Name handles apostrophe in name | Manual — PASS
TC-0237 | Create Account | Verify First Name handles 100-character input | Manual — PASS
TC-0238 | Create Account | Verify First Name handles numeric input | Manual — PASS
TC-0239 | Create Account | Verify First Name handles special characters | Manual — PASS
TC-0240 | Create Account | Verify Last Name handles multi-word surname | Manual — PASS
TC-0241 | Create Account | Verify Last Name handles HTML/script injection | Manual — PASS
TC-0242 | Create Account | Verify Email field rejects email without @ symbol | Manual — PASS
TC-0243 | Create Account | Verify Email field rejects email without domain TLD | Manual — PASS
TC-0244 | Create Account | Verify Email field rejects email without local part | Manual — PASS
TC-0245 | Create Account | Verify Email field rejects email with spaces in local part | Manual — PASS
TC-0246 | Create Account | Verify Email field accepts a valid email | Manual — PASS
TC-0247 | Create Account | Verify modal info icon (ⓘ) is visible | Manual — PASS
TC-0248 | Create Account | Verify modal displays the entered full name | Manual — PASS
TC-0249 | Create Account | Verify "will be displayed on the certificate" message is shown | Manual — PASS
TC-0250 | Create Account | "Edit name" button is visible and returns to form | Manual — PASS
TC-0251 | Create Account | "Confirm name" button is visible and advances to password screen | Manual — PASS
TC-0252 | Create Account | Verify name in modal reflects updates after editing | Manual — PASS
TC-0253 | Create Account | Verify modal background is dimmed (overlay visible) | Manual — PASS
TC-0254 | Create Account | "Set your password" heading is visible | Manual — PASS
TC-0255 | Create Account | Verify Password field is visible and masks the input | Manual — PASS
TC-0256 | Create Account | Verify eye icon toggles password visibility | Manual — PASS
TC-0257 | Create Account | Verify Confirm Password field is visible and masks input | Manual — PASS
TC-0258 | Create Account | Verify Confirm Password field has its own eye icon | Manual — PASS
TC-0259 | Create Account | "Password Requirements:" heading is visible | Manual — PASS
TC-0260 | Create Account | Criterion "Minimum 8 characters" is listed | Manual — PASS
TC-0261 | Create Account | Criterion "One capital letter" is listed | Manual — PASS
TC-0262 | Create Account | Criterion "One number" is listed | Manual — PASS
TC-0263 | Create Account | Criterion "One special character" is listed | Manual — PASS
TC-0264 | Create Account | Verify all 4 criteria turn green when strong password is entered | Manual — PASS
TC-0265 | Create Account | Verify too-short password fails the 8-char criterion | Manual — PASS
TC-0266 | Create Account | Verify password without uppercase fails the capital-letter criterion | Manual — PASS
TC-0267 | Create Account | Verify password without number fails the number criterion | Manual — PASS
TC-0268 | Create Account | Verify password without special character fails the special-char criterion | Manual — PASS
TC-0269 | Create Account | Verify password without lowercase still passes (if not required) | Manual — PASS
TC-0270 | Create Account | Verify matching passwords are accepted | Manual — PASS
TC-0271 | Create Account | Verify mismatched passwords show an error | Manual — PASS
TC-0272 | Create Account | Verify Next button is disabled with empty password fields | Manual — PASS
TC-0273 | Create Account | Verify Next button is enabled with matching valid passwords | Manual — PASS
TC-0274 | Create Account | Verify Next button submits and creates the account | Manual — PASS
TC-0275 | Create Account | Create Account form renders correctly on mobile (390 × 844) | Manual — PASS
TC-0276 | Create Account | Create Account form renders correctly on tablet (768 × 1024) | Manual — PASS
TC-0277 | Create Account | Create Account form renders correctly on desktop (1440 × 900) | Manual — PASS
TC-0278 | Create Account | Name Confirmation modal renders correctly on mobile | Manual — PASS
TC-0279 | Create Account | Set Password screen renders correctly on mobile | Manual — PASS
TC-0280 | Create Account | No console errors during Create Account flow | Manual — PASS
TC-0281 | Create Account | Verify back-navigation in browser does not break the flow | Manual — PASS
TC-0282 | Create Account | Verify page reload mid-flow handles state gracefully | Manual — PASS
TC-0283 | Create Account | Verify duplicate-email registration shows appropriate error | Manual — PASS
TC-0284 | Create Account | Verify successful account creation reaches the post-signup destination | Manual — PASS
TC-0285 | Login | Verify Aastrika Sphere logo is displayed | Manual — PASS
TC-0286 | Login | Verify Back arrow button is visible and clickable | Manual — PASS
TC-0287 | Login | Verify Help button opens the chat support modal | Manual — PASS
TC-0288 | Login | Verify "Welcome!" heading is displayed | Manual — PASS
TC-0289 | Login | Verify sub-heading "Login with your Aastrika account" is displayed | Manual — PASS
TC-0290 | Login | Verify "Login with OTP" radio is visible and selected by default | Manual — PASS
TC-0291 | Login | Verify "Login with Password" radio switches to password mode | Manual — PASS
TC-0292 | Login | Verify toggling back to OTP hides the password field | Manual — PASS
TC-0293 | Login | Verify identifier field accepts a valid phone number | Manual — PASS
TC-0294 | Login | Verify identifier field accepts a valid email address | Manual — PASS
TC-0295 | Login | Verify "Get OTP" button is visible | Manual — PASS
TC-0296 | Login | "Get OTP" button is disabled when input is empty | Manual — PASS
TC-0297 | Login | "Get OTP" button is clickable with valid input | Manual — PASS
TC-0298 | Login | Verify identifier field is visible in password mode | Manual — PASS
TC-0299 | Login | Verify password field is visible and masks input | Manual — PASS
TC-0300 | Login | Verify eye icon toggles password visibility | Manual — PASS
TC-0301 | Login | "Forgot Password?" link is visible and clickable | Manual — PASS
TC-0302 | Login | "Login" button submits credentials | Manual — PASS
TC-0303 | Login | "or" separator is displayed | Manual — PASS
TC-0304 | Login | "Create an Account" button is visible and navigates to signup | Manual — PASS
TC-0305 | Login | Modal heading "Aastrika Sphere chat support" is displayed | Manual — PASS
TC-0306 | Login | "Chat with us on WhatsApp" button opens WhatsApp | Manual — PASS
TC-0307 | Login | "Chat with us" button opens in-app chat | Manual — PASS
TC-0308 | Login | Modal close (×) button dismisses the modal | Manual — PASS
TC-0309 | Login | Identifier field handles empty input | Manual — PASS
TC-0310 | Login | Identifier field handles whitespace-only input | Manual — PASS
TC-0311 | Login | Identifier field handles a single character | Manual — PASS
TC-0312 | Login | Identifier field handles 10-digit phone | Manual — PASS
TC-0313 | Login | Identifier field handles phone with country code | Manual — PASS
TC-0314 | Login | Identifier field handles a standard email address | Manual — PASS
TC-0315 | Login | Identifier field handles uppercase email | Manual — PASS
TC-0316 | Login | Identifier field handles special characters only | Manual — PASS
TC-0317 | Login | Identifier field handles very long input (256 chars) | Manual — PASS
TC-0318 | Login | Identifier field is safe against XSS payload | Manual — PASS
TC-0319 | Login | Page renders correctly on mobile viewport (390 × 844) | Manual — PASS
TC-0320 | Login | Page renders correctly on tablet viewport (768 × 1024) | Manual — PASS
TC-0321 | Login | Page renders correctly on desktop viewport (1440 × 900) | Manual — PASS
TC-0322 | Login | No console errors are thrown on page load | Manual — PASS
TC-0323 | Login | Page title contains "Aastrika" or "Sphere" | Manual — PASS
TC-0324 | Home (Authenticated) | Verify Aastrika Sphere logo is visible | Manual — PASS
TC-0325 | Home (Authenticated) | Verify logo click navigates to Home page | Manual — PASS
TC-0326 | Home (Authenticated) | Verify search bar is visible with placeholder | Manual — PASS
TC-0327 | Home (Authenticated) | Verify search bar accepts text input | Manual — PASS
TC-0328 | Home (Authenticated) | Verify search submission with Enter key triggers results | Manual — PASS
TC-0329 | Home (Authenticated) | Verify search icon is visible inside the search bar | Manual — PASS
TC-0330 | Home (Authenticated) | Verify dark mode toggle is visible in header | Manual — PASS
TC-0331 | Home (Authenticated) | Verify dark mode toggle switches the theme | Manual — PASS
TC-0332 | Home (Authenticated) | Verify "Home" nav link is present and active | Manual — PASS
TC-0333 | Home (Authenticated) | Verify "My Courses" nav link navigates correctly | Manual — PASS
TC-0334 | Home (Authenticated) | Verify "Competency" nav link navigates correctly | Manual — PASS
TC-0335 | Home (Authenticated) | Verify "Account" nav link opens the Account section | Manual — PASS
TC-0336 | Home (Authenticated) | Verify notification bell icon is visible in header | Manual — PASS
TC-0337 | Home (Authenticated) | Verify notification bell click opens notifications panel | Manual — PASS
TC-0338 | Home (Authenticated) | Verify "Welcome !" greeting is visible | Manual — PASS
TC-0339 | Home (Authenticated) | Verify user's display name is shown below "Welcome !" | Manual — PASS
TC-0340 | Home (Authenticated) | Verify "Start Learning" subtitle is visible | Manual — PASS
TC-0341 | Home (Authenticated) | Verify hero carousel banner is visible on the right | Manual — PASS
TC-0342 | Home (Authenticated) | Verify "Watch how Sphere works" headline is visible in carousel | Manual — PASS
TC-0343 | Home (Authenticated) | Verify "Watch now" button is visible and clickable | Manual — PASS
TC-0344 | Home (Authenticated) | Verify carousel pagination dots are visible | Manual — PASS
TC-0345 | Home (Authenticated) | Verify clicking a pagination dot switches the carousel slide | Manual — PASS
TC-0346 | Home (Authenticated) | Verify "CONTINUE LEARNING" section heading is visible (if user has in-progress courses) | Manual — PASS
TC-0347 | Home (Authenticated) | Verify Continue Learning section is hidden for new users | Manual — PASS
TC-0348 | Home (Authenticated) | Verify "View All" link is visible next to Continue Learning heading | Manual — PASS
TC-0349 | Home (Authenticated) | Verify clicking a Continue Learning card opens the course | Manual — PASS
TC-0350 | Home (Authenticated) | Verify "CNE COURSES" section heading is visible | Manual — PASS
TC-0351 | Home (Authenticated) | Verify "View All" link is visible for CNE Courses | Manual — PASS
TC-0352 | Home (Authenticated) | Verify CNE Courses section displays at least 4 course cards | Manual — PASS
TC-0353 | Home (Authenticated) | Verify each CNE card displays course title | Manual — PASS
TC-0354 | Home (Authenticated) | Verify CNE points badge is displayed on each card | Manual — PASS
TC-0355 | Home (Authenticated) | Verify course star rating is visible on each card | Manual — PASS
TC-0356 | Home (Authenticated) | Verify provider tag is shown on each card | Manual — PASS
TC-0357 | Home (Authenticated) | Verify clicking a CNE card opens the course detail page | Manual — PASS
TC-0358 | Home (Authenticated) | Verify "View All" CNE click navigates to all CNE courses | Manual — PASS
TC-0359 | Home (Authenticated) | Verify CNE Courses section can be horizontally scrolled / paginated | Manual — PASS
TC-0360 | Home (Authenticated) | Verify "Register for a course" card is visible | Manual — PASS
TC-0361 | Home (Authenticated) | Verify "Register for a course" subtitle text is visible | Manual — PASS
TC-0362 | Home (Authenticated) | Verify "Take the course" card is visible | Manual — PASS
TC-0363 | Home (Authenticated) | Verify "Take the course" subtitle text is visible | Manual — PASS
TC-0364 | Home (Authenticated) | Verify "Get certified" card is visible | Manual — PASS
TC-0365 | Home (Authenticated) | Verify "Get certified" subtitle text is visible | Manual — PASS
TC-0366 | Home (Authenticated) | Verify clicking "Register for a course" card triggers navigation | Manual — PASS
TC-0367 | Home (Authenticated) | Verify clicking "Take the course" card triggers navigation | Manual — PASS
TC-0368 | Home (Authenticated) | Verify clicking "Get certified" card triggers navigation | Manual — PASS
TC-0369 | Home (Authenticated) | Verify Aastrika Sphere footer logo is visible | Manual — PASS
TC-0370 | Home (Authenticated) | Verify "Quick Links" heading is visible | Manual — PASS
TC-0371 | Home (Authenticated) | Verify "Privacy policy" link is visible and clickable | Manual — PASS
TC-0372 | Home (Authenticated) | Verify "Terms of Use" link is visible and clickable | Manual — PASS
TC-0373 | Home (Authenticated) | Verify "Help & Contact" heading is visible | Manual — PASS
TC-0374 | Home (Authenticated) | Verify support email link is visible | Manual — PASS
TC-0375 | Home (Authenticated) | Verify support email click opens mail client | Manual — PASS
TC-0376 | Home (Authenticated) | Verify "Talk to us on WhatsApp" button is visible | Manual — PASS
TC-0377 | Home (Authenticated) | Verify WhatsApp button opens WhatsApp chat | Manual — PASS
TC-0378 | Home (Authenticated) | Verify "Additional Links" heading is visible | Manual — PASS
TC-0379 | Home (Authenticated) | Verify Aastrika Foundation link is visible with URL | Manual — PASS
TC-0380 | Home (Authenticated) | Verify Aastrika Foundation link opens in new tab | Manual — PASS
TC-0381 | Home (Authenticated) | Verify Twitter / X social icon is visible | Manual — PASS
TC-0382 | Home (Authenticated) | Verify Facebook social icon is visible | Manual — PASS
TC-0383 | Home (Authenticated) | Verify Instagram social icon is visible | Manual — PASS
TC-0384 | Home (Authenticated) | Verify LinkedIn social icon is visible | Manual — PASS
TC-0385 | Home (Authenticated) | Verify copyright notice is visible | Manual — PASS
TC-0386 | Home (Authenticated) | Verify copyright year is current | Manual — PASS
TC-0387 | Home (Authenticated) | Verify page title contains "Aastrika" or "Sphere" | Manual — PASS
TC-0388 | Home (Authenticated) | Verify no JavaScript console errors on page load | Manual — PASS
TC-0389 | Home (Authenticated) | Verify page renders correctly on mobile viewport (390 × 844) | Manual — PASS
TC-0390 | Home (Authenticated) | Verify page renders correctly on tablet viewport (768 × 1024) | Manual — PASS
TC-0391 | Home (Authenticated) | Verify page renders correctly on desktop viewport (1440 × 900) | Manual — PASS
TC-0392 | Home (Authenticated) | Verify header stays sticky / fixed on scroll | Manual — PASS
TC-0393 | Home (Authenticated) | Verify footer is visible after scrolling to the bottom | Manual — PASS
TC-0394 | Home (Authenticated) | Verify accessing /page/home without login redirects to /public/login | Manual — PASS
TC-0395 | Home (Authenticated) | Verify Home page loads only for authenticated users | Manual — PASS
TC-0396 | Home (Authenticated) | Verify session persists across page reloads | Manual — PASS
TC-0397 | Public Page | Verify clicking on login button | Manual — PASS
TC-0398 | Public Page | Verify clicking on create account button | Manual — PASS
TC-0399 | Public Page | Verify by clicking on " Watch tutorials on how sphere works " | Manual — PASS
TC-0400 | Public Page | Verify by clicking on courses in the public page | Manual — PASS
TC-0401 | Public Page | Verify by clicking on " Start now " button | Manual — PASS
TC-0402 | Public Page | Verify by clicking on " Read Chapter " button | Manual — PASS
TC-0403 | Public Page | Verify by clicking on device back button when in RMC chapter | Manual — PASS
TC-0404 | Public Page | Verify by clicking on youtube icon in " How does it work " | Manual — PASS
TC-0405 | Public Page | Verify by clicking on " Register for a course " field | Manual — PASS
TC-0406 | Public Page | Verify by clicking on " Take the course " field | Manual — PASS
TC-0407 | Public Page | Verify by clicking on " Get certified " field | Manual — PASS
TC-0408 | Public Page | Verify by clicking on " Start Today " button | Manual — PASS
TC-0409 | Public Page | Verify by clicking on " Privacy Policy " | Manual — PASS
TC-0410 | Public Page | Verify by clicking on " Terms of use " | Manual — PASS
TC-0411 | Public Page | Verify by clicking on " Support@aastrika.org " | Manual — PASS
TC-0412 | Public Page | Verify by clicking on " Talk to us on Whatsapp " | Manual — PASS
TC-0413 | Public Page | Verify by clicking on " Additional links " | Manual — PASS
TC-0414 | Login | Verify by clicking on login button should open login page | Manual — PASS
TC-0415 | Login | Verify by clicking on " X " icon is closing the page | Manual — PASS
TC-0416 | Login | Verify if the radio buttons of login with OTP and Login with password is working or not | Manual — PASS
TC-0417 | Login | Verify by giving wrong email address in login with OTP | Manual — PASS
TC-0418 | Login | Verfy by clicking on " Get OTP " without filling email/password | Manual — PASS
TC-0419 | Login | Verify login with valid email and password | Manual — PASS
TC-0420 | Login | Verify login with valid email and invalid password | Manual — PASS
TC-0421 | Login | Verify login with invalid email and invalid password | Manual — PASS
TC-0422 | Login | Verify clicking on sign in with out filling email and password | Manual — PASS
TC-0423 | Login | Verify by clicking on create account button in login page | Manual — PASS
TC-0424 | Login | Verify by clicking on " Get help on whatsapp " | Manual — PASS
TC-0425 | Login | Verify by clicking on Get OTP should land on OTP page | Manual — PASS
TC-0426 | Login | Verify by cliking on " Submit " should land on T&C page | Manual — PASS
TC-0427 | Login | Verify by clicking on " resend OTP " should resend the OTP | Manual — PASS
TC-0428 | Login | Verify by clicking on " Get help on whatsapp " | Manual — PASS
TC-0429 | Login | Verify by clicking on " Back to aastrika sphere " | Manual — PASS
TC-0430 | Create Account | Verify by clicking on create account button | Manual — PASS
TC-0431 | Create Account | Verify if the default languge is " English " | Manual — PASS
TC-0432 | Create Account | Verify if the application back button is taking user to the public page | Manual — PASS
TC-0433 | Create Account | Verfiy if clicking on aastrika logo is taking user to the public page | Manual — PASS
TC-0434 | Create Account | Verify if both radio buttons are working to select the language | Manual — PASS
TC-0435 | Create Account | Verify when clicking on Hindi all the Info is translating to Hindi language | Manual — PASS
TC-0436 | Create Account | Verify if save button is clickable or not | Manual — PASS
TC-0437 | Create Account | Verify by clicking on create account button | Manual — PASS
TC-0438 | Create Account | Verify filling up all valid details in create account page and click on next button | Manual — PASS
TC-0439 | Create Account | Verify filling up all wtih Invalid email id in signup page and click on next button | Manual — PASS
TC-0440 | Create Account | Verify if the next button is highlighting when given all the valid details | Manual — PASS
TC-0441 | Create Account | Verify if clicking on application back button is landing to language selection page | Manual — PASS
TC-0442 | Create Account | Verify by entering the right OTP and click on next | Manual — PASS
TC-0443 | Create Account | Verify by clicking on " Click here " to resend the OTP to registerd email/mobile number | Manual — PASS
TC-0444 | Create Account | Verify if the wrong OTP enters should give correct toast | Manual — PASS
TC-0445 | Home (Authenticated) | Verify by clicking on aastrika logo should refresh the page | Manual — PASS
TC-0446 | Home (Authenticated) | Verify by clicking on get help icon | Manual — PASS
TC-0447 | Home (Authenticated) | Verify if both the Whatsapp and freshchat icon appears after the loader | Manual — PASS
TC-0448 | Home (Authenticated) | Verify by clicking on " X " button user should land in private home page | Manual — PASS
TC-0449 | Home (Authenticated) | Verify by clicking on " Watch tutorials on how sphere works " | Manual — PASS
TC-0450 | Home (Authenticated) | Verify by clicking on any courses should open " Tell us more about you " page for 1st time | Manual — PASS
TC-0451 | Home (Authenticated) | Verify if all the fields are filled with valid details | Manual — PASS
TC-0452 | Home (Authenticated) | Verify after entering all the valid fields only " next " button should highlighted | Manual — PASS
TC-0453 | Home (Authenticated) | Verify if " Next " button is clickable or not | Manual — PASS
TC-0454 | Home (Authenticated) | Verify if user can select the background of their choice | Manual — PASS
TC-0455 | Home (Authenticated) | Verify if all the blocks are clickable or not | Manual — PASS
TC-0456 | Home (Authenticated) | Verify by clicking on respective blocks is opening respective details about background | Manual — PASS
TC-0457 | Home (Authenticated) | Verify by clicking on change is landing user to the background blocks page | Manual — PASS
TC-0458 | Home (Authenticated) | Verify after entering all the valid fields only " Done " button should highlighted | Manual — PASS
TC-0459 | Home (Authenticated) | Verify cliking on done should take user to the course which clicked before | Manual — PASS
TC-0460 | Home (Authenticated) | Verify by clicking on any courses should open TOC page | Manual — PASS
TC-0461 | Home (Authenticated) | Verify by clicking on " View all course " Should display all courses | Manual — PASS
TC-0462 | Home (Authenticated) | Verify by clicking on youtube icon in " How does it work " | Manual — PASS
TC-0463 | Home (Authenticated) | Verify by clicking on " Register for a course " field | Manual — PASS
TC-0464 | Home (Authenticated) | Verify by clicking on " Take the course " field | Manual — PASS
TC-0465 | Home (Authenticated) | Verify by clicking on " Get certified " field | Manual — PASS
TC-0466 | Home (Authenticated) | Verify when user in home page " Home " icon should be highlighted | Manual — PASS
TC-0467 | Course TOC | Verify by cliking on application back icon is taking user to the homepage | Manual — PASS
TC-0468 | Course TOC | Verify by clicking on Org should land in organization page | Manual — PASS
TC-0469 | Course TOC | Verify by clicking on details shlould display the course details in popup | Manual — PASS
TC-0470 | Course TOC | Verify by clicking on " X " button should close the details popup | Manual — PASS
TC-0471 | Course TOC | Verify by clicking on " Certificate " button should give popup saying to complete the course | Manual — PASS
TC-0472 | Course TOC | Verify by clicking on " Close " button should close the popup | Manual — PASS
TC-0473 | Course TOC | Verify by clicking on " Share " button | Manual — PASS
TC-0474 | Course TOC | Verify by clicking on " Start " should start the course | Manual — PASS
TC-0475 | Course TOC | Verify by clicking on " License Terms " link | Manual — PASS
TC-0476 | Course TOC | Verify by clicking on resources should start the resources | Manual — PASS
TC-0477 | Course TOC | Verify by clicking on SCROM video should open it in web view | Manual — PASS
TC-0478 | Course TOC | Verify by clicking on " X " button should close the SCROM | Manual — PASS
TC-0479 | Course TOC | Verify by clicking on " PDF " resources should open | Manual — PASS
TC-0480 | Course TOC | Verify by clicking on " Full Screen " should open the resource in full screen | Manual — PASS
TC-0481 | Course TOC | Verify by clicking on " < " and " > " icon should take user to the respective pages | Manual — PASS
TC-0482 | Course TOC | Verify by scrolling the pdf for next and previous pages | Manual — PASS
TC-0483 | Course TOC | Verify by pinching the pdf for zoom in and zoom out | Manual — PASS
TC-0484 | Course TOC | Verify when pdf's at last page should get update with green tick | Manual — PASS
TC-0485 | Course TOC | Verify by clicking on " Next " and " Previous " icon should take user to the respective resources | Manual — PASS
TC-0486 | Course TOC | Veify by clicking on assessment should open the assessment | Manual — PASS
TC-0487 | Course TOC | Verify by clicking on " Start " should start the assessment | Manual — PASS
TC-0488 | Course TOC | Verify by clicking on " X " should close the assessment | Manual — PASS
TC-0489 | Course TOC | Verify by clicking on checkbox should select the answers | Manual — PASS
TC-0490 | Course TOC | Verify by clicking on back button should give pop up saying " Do you want to Exit ? " | Manual — PASS
TC-0491 | Course TOC | Veify by clicking on " No " should restart the assessment | Manual — PASS
TC-0492 | Course TOC | Verify by clicking on " Yes " Should close the pop up | Manual — PASS
TC-0493 | Course TOC | Verify by clicking on " Next " should move to next question | Manual — PASS
TC-0494 | Course TOC | Verify by clicking on " Back " should move to back question | Manual — PASS
TC-0495 | Course TOC | Veriy if " Continue " button is highlighted only when user met the required percentage | Manual — PASS
TC-0496 | Course TOC | Verify by clicking on " Retake Assessment " should restart the assessment | Manual — PASS
TC-0497 | Course TOC | Verify by clicking on back button should give pop up saying " Do you want to Exit ? " | Manual — PASS
TC-0498 | Course TOC | Verify by completing the entire course should give pop up for " Completion Animation " | Manual — PASS
TC-0499 | My Courses | Verify by clicking on " My course " should highlight in nav bar | Manual — PASS
TC-0500 | My Courses | Verify by clicking on " My course " should open the new tab | Manual — PASS
TC-0501 | My Courses | Verify that the started courses should display in the started courses | Manual — PASS
TC-0502 | My Courses | Verify that the Designation courses should display under " For you " | Manual — PASS
TC-0503 | My Courses | Verify that the completed courses should display under " Completed " tab | Manual — PASS
TC-0504 | My Courses | Verify by clicking on Completed course should display " Start Again " in TOC page | Manual — PASS
TC-0505 | My Courses | Verify by clicking on " Certificate " Should start downloading the certificate | Manual — PASS
TC-0506 | Competency Dashboard | Verify by clicking on " Competency " should highlight in nav bar | Manual — PASS
TC-0507 | Competency Dashboard | Verify by clicking on " Competency " should open the tab with passbook | Manual — PASS
TC-0508 | Competency Dashboard | Verify by clicking on " Required " should display all the self assessment list | Manual — PASS
TC-0509 | Competency Dashboard | Verify by clicking on " assess " should Open Pop up for the self assessment | Manual — PASS
TC-0510 | Competency Dashboard | Verify By clicking on " Start Now " should start the self assessment | Manual — PASS
TC-0511 | Competency Dashboard | Verify by clicking on " X " should close the Self Assessment | Manual — PASS
TC-0512 | Competency Dashboard | Verify by clicking on checkbox should select the answers | Manual — PASS
TC-0513 | Competency Dashboard | Verify by clicking on back button should give pop up saying " Do you want to Exit ? " | Manual — PASS
TC-0514 | Competency Dashboard | Veify by clicking on " No " should restart the assessment | Manual — PASS
TC-0515 | Competency Dashboard | Verify by clicking on " Yes " Should close the pop up | Manual — PASS
TC-0516 | Competency Dashboard | Verify by clicking on " Next " should move to next question | Manual — PASS
TC-0517 | Competency Dashboard | Verify by clicking on " Back " should move to back question | Manual — PASS
TC-0518 | Competency Dashboard | Veriy If the message " You didn't pass the assessment " when user hasn't met the required percentage | Manual — PASS
TC-0519 | Competency Dashboard | Verify by clicking on " View relevant Courses " should take to relevant courses | Manual — PASS
TC-0520 | Competency Dashboard | Verify by clicking on " Go to Competency Dashboard " should take to passbook page | Manual — PASS
TC-0521 | Competency Dashboard | Verify by clicking on " View Courses " should display all the courses related to self assessment | Manual — PASS
TC-0522 | Competency Dashboard | Verify by clicking on dropdown button should display the completed self assessment in passbook | Manual — PASS
TC-0523 | Competency Dashboard | Verify by clicking on levels should display the completed self assessment in passbook | Manual — PASS
TC-0524 | Competency Dashboard | Verify by clicking on " Job Description " should display all the Roles courses | Manual — PASS
TC-0525 | Competency Dashboard | Verify by clicking on dropdown button should display the " activities " and " competency " in the roles | Manual — PASS
TC-0526 | Competency Dashboard | Verify by clicking on dropdown button in competencies should display all the levels | Manual — PASS
TC-0527 | Competency Dashboard | Verify by clicking on " assess " should Open Pop up for the self assessment | Manual — PASS
TC-0528 | Competency Dashboard | Verify By clicking on " Start Now " should start the self assessment | Manual — PASS
TC-0529 | Competency Dashboard | Verify by clicking on " X " should close the Self Assessment | Manual — PASS
TC-0530 | Competency Dashboard | Verify by clicking on checkbox should select the answers | Manual — PASS
TC-0531 | Competency Dashboard | Verify by clicking on back button should give pop up saying " Do you want to Exit ? " | Manual — PASS
TC-0532 | Competency Dashboard | Veify by clicking on " No " should restart the assessment | Manual — PASS
TC-0533 | Competency Dashboard | Verify by clicking on " Yes " Should close the pop up | Manual — PASS
TC-0534 | Competency Dashboard | Verify by clicking on " Next " should move to next question | Manual — PASS
TC-0535 | Competency Dashboard | Verify by clicking on " Back " should move to back question | Manual — PASS
TC-0536 | Competency Dashboard | Veriy If the message " You didn't pass the assessment " when user hasn't met the required percentage | Manual — PASS
TC-0537 | Competency Dashboard | Verify by clicking on " View relevant Courses " should take to relevant courses | Manual — PASS
TC-0538 | Competency Dashboard | Verify by clicking on " Go to Competency Dashboard " should take to passbook page | Manual — PASS
TC-0539 | Competency Dashboard | Verify by clicking on " View Courses " should display all the courses related to self assessment | Manual — PASS
TC-0540 | Search | Verify by clicking on " Search Bar " should display recently published courses | Manual — PASS
TC-0541 | Search | Verify by clicking on " Search Bar " should display all the courses | Manual — PASS
TC-0542 | Search | Verify if the selected language is selected as english | Manual — PASS
TC-0543 | Search | Verify by clicking on search icon should refresh the page | Manual — PASS
TC-0544 | Search | Verify by clicking on search field should user able to enter the items | Manual — PASS
TC-0545 | Search | Verify by entering the field in Hindi language should display list of Hindi courses related to the term | Manual — PASS
TC-0546 | Search | Verify by clicking on select langugae should be able to select the language | Manual — PASS
TC-0547 | Search | Verify by clicking on aastrika logo Should take user to the home page | Manual — PASS
TC-0548 | Account | Verify by clicking on " Account " should highlight in nav bar | Manual — PASS
TC-0549 | Account | Verify by clicking on " Account " should display all the settings related to profile details | Manual — PASS
TC-0550 | Account | Verify by clicking on back button Should take user to the home page | Manual — PASS
TC-0551 | Account | Verify by clicking on edit icon in profile pic should open the pop up for different images | Manual — PASS
TC-0552 | Account | Verify by clicking on " X " should close the profile picture | Manual — PASS
TC-0553 | Account | Verify by clicking on " Add your own Image " should use user to select his own image | Manual — PASS
TC-0554 | Account | Verify by clicking on " Language Preferance " should open new tab to select the language | Manual — PASS
TC-0555 | Account | Verify by clicking on both the radio buttons and save the button | Manual — PASS
TC-0556 | Account | Verify by clicking on back button Should take user to the account page | Manual — PASS
TC-0557 | Account | Verify by clicking on save button should take user to the home page | Manual — PASS
TC-0558 | Account | Verify by clicking on the Hindi language should translate all the words to Hindi | Manual — PASS
TC-0559 | Account | Verify by clicking on " My certificates " should display all the completed certificates | Manual — PASS
TC-0560 | Account | Verify by clicking on download icon should be able to download the certificate | Manual — PASS
TC-0561 | Account | Verify by clicking on " Profile Details " should display all the details related to profile | Manual — PASS
TC-0562 | Account | Verify by clicking on edit icon in personal details should open edit tab | Manual — PASS
TC-0563 | Account | Verify by clicking on DOB field should be able to change | Manual — PASS
TC-0564 | Account | Verify by clicking on " Nationality " field should be able to edit | Manual — PASS
TC-0565 | Account | Verify by clicking " Mother Tongue " field should be able to edit | Manual — PASS
TC-0566 | Account | Verify by clicking on " gender " drop down should be able to select | Manual — PASS
TC-0567 | Account | Verify by clicking on " Martial Status " drop down should be able to select | Manual — PASS
TC-0568 | Account | Verify by clicking on " Phone number " should be able to edit | Manual — PASS
TC-0569 | Account | Verify by clicking on " Address " should be able to edit | Manual — PASS
TC-0570 | Account | Verfiy by clicking on " Pincode " should be able to edit | Manual — PASS
TC-0571 | Account | Verify after entering any field " Save " Button should be enabled | Manual — PASS
TC-0572 | Account | Verify by clicking on " Organization Details " Should display all the details about organization | Manual — PASS
TC-0573 | Account | Verify by clicking on edit icon in organization details should open edit tab in new page | Manual — PASS
TC-0574 | Account | Verify by clicking on " Desigation " drop down should be able to select | Manual — PASS
TC-0575 | Account | Verify after entering any field " Save " Button should be enabled | Manual — PASS
TC-0576 | Account | Verify by clicking on " Academic Details " should open new tab | Manual — PASS
TC-0577 | Account | Verify by clicking on " + " to add the academic details | Manual — PASS
TC-0578 | Account | Verify by clicking on " Grade/Degree " drop down should be able to select | Manual — PASS
TC-0579 | Account | Verify by clicking on " Institution Name " field should be able to edit | Manual — PASS
TC-0580 | Account | Verify by clicking on " Year of passing " field should be able to edit | Manual — PASS
TC-0581 | Account | Verify if save button is enabled only when given valid details | Manual — PASS
TC-0582 | Account | Verify by clicking on back button Should take user to the account page | Manual — PASS
TC-0583 | Logout | Verify by clicking on " Logout " button is clickable or not | Manual — PASS
TC-0584 | Logout | Verify by clicking on " Logout " button pop up should be displayed to make sure | Manual — PASS
TC-0585 | Logout | Verify by clicking on " No " should stay in the account page | Manual — PASS
TC-0586 | Logout | Verify by clciking on " Yes " should naviagte to public home page | Manual — PASS
TC-0587 | Course TOC | Veify by clicking on quiz should open the quiz | Manual — PASS
TC-0588 | Course TOC | Verify by clicking on " Start Now " should start the quiz | Manual — PASS
TC-0589 | Course TOC | Verify by clicking on " X " should close the quiz | Manual — PASS
TC-0590 | Course TOC | Verify by clicking on checkbox should select the answers | Manual — PASS
TC-0591 | Course TOC | Veify by clicking on " No, Continue quiz " should restart the quiz | Manual — PASS
TC-0592 | Course TOC | Verify by clicking on " Yes " Should close the pop up and navigate to TOC page | Manual — PASS
TC-0593 | Course TOC | Verify by clicking on " Submit " should move to next question | Manual — PASS
TC-0594 | Course TOC | Verify by clicking on " Restart " should restart the quiz | Manual — PASS
TC-0595 | Course TOC | Veriy if " continue " button is highlighted even when user not met the required percentage | Manual — PASS
TC-0596 | Course TOC | Verify by clicking on " Retake quiz " should restart the quiz | Manual — PASS
TC-0597 | Course TOC | Veriy the required percentage is displaying as " 0% " in TOC and module tab | Manual — PASS
TC-0598 | Notifications | Verify clicking on notification icon when no notification is received | Manual — PASS
TC-0599 | Notifications | Verify clicking on notification icon when notification is received | Manual — PASS
TC-0600 | Notifications | Verify clicking on any one received notification | Manual — PASS
TC-0601 | Notifications | Verify clicking on mark all as read button when notifications are present | Manual — PASS
TC-0602 | Login | Verify login fails with invalid email format | Manual — PASS
TC-0603 | Login | Verify login fails with empty credentials | Manual — PASS
TC-0604 | Login | Verify login fails with wrong OTP (phone-based) | Manual — PASS
TC-0605 | Login | Verify multiple failed login attempts trigger appropriate handling | Manual — PASS
TC-0606 | Login | Verify rapid clicking of Login button does not submit multiple times | Manual — PASS
TC-0607 | Login | Verify session expiry redirects to login | Manual — PASS
TC-0608 | Create Account | Verify signup fails with already-registered email | Manual — PASS
TC-0609 | Create Account | Verify signup fails with weak password | Manual — PASS
TC-0610 | Create Account | Verify mismatched password confirmation is blocked | Manual — PASS
TC-0611 | Create Account | Verify Terms checkbox required for signup | Manual — PASS
TC-0612 | Course TOC | Verify course progress is preserved if app force-closed mid-video | Manual — PASS
TC-0613 | Course TOC | Verify graceful handling of network interruption during video | Manual — PASS
TC-0614 | Search | Verify search with empty query shows guidance or no results | Manual — PASS
TC-0615 | Search | Verify search for nonexistent term shows empty state | Manual — PASS
TC-0616 | Search | Verify search handles special characters safely | Manual — PASS
TC-0617 | Notifications | Verify empty state for new users with no notifications | Manual — PASS
TC-0618 | Notifications | Verify unread count badge updates after reading notifications | Manual — PASS
TC-0619 | Home (Authenticated) | Verify browser back button navigation works correctly | Manual — PASS
TC-0620 | Home (Authenticated) | Verify page refresh preserves user session and state | Manual — PASS
TC-0621 | Account | Verify XSS attempt in profile fields is sanitized | Manual — PASS
TC-0622 | Account | Verify special characters in name are accepted safely | Manual — PASS
TC-0623 | Public Page | Verify public page renders correctly in Firefox | Manual — PASS
TC-0624 | Public Page | Verify public page renders correctly in Safari | Manual — PASS
TC-0625 | Public Page | Verify public page renders correctly in Edge | Manual — PASS
TC-0626 | Home (Authenticated) | Verify all interactive elements are keyboard-accessible | Manual — PASS
TC-0627 | Home (Authenticated) | Verify images have meaningful alt text | Manual — PASS
TC-0628 | Home (Authenticated) | Verify color contrast meets WCAG AA | Manual — PASS