## Coverage Report
Aastrika Sphere — Test Coverage Report (Manual + Automation)
560 must-run cases · Manual = Done (documented suite) · Automation marked Done / To Add · 06 July 2026
Automated (Done): 180 · To Add to Automation: 152 (Tier 1: 70 · Tier 2: 82) · Confirm: 171 · Manual only: 57
Test Case ID | Module | Section | Test Case Description | Priority | Manual Testing | Automation | Coverage Note
TC-0548 | Account | Account | Verify by clicking on " Account " should highlight in nav bar | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0549 | Account | Account | Verify by clicking on " Account " should display all the settings related to profile details | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0560 | Account | My Certificates | Verify by clicking on download icon should be able to download the certificate | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0564 | Account | Profile Details | Verify by clicking on " Nationality " field should be able to edit | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0565 | Account | Profile Details | Verify by clicking " Mother Tongue " field should be able to edit | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0566 | Account | Profile Details | Verify by clicking on " gender " drop down should be able to select | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0567 | Account | Profile Details | Verify by clicking on " Martial Status " drop down should be able to select | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0569 | Account | Profile Details | Verify by clicking on " Address " should be able to edit | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0621 | Account | Account - Negative | Verify XSS attempt in profile fields is sanitized | High | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0622 | Account | Account - Negative | Verify special characters in name are accepted safely | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0519 | Competency Dashboard | Required | Verify by clicking on " View relevant Courses " should take to relevant courses | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0537 | Competency Dashboard | Job Description | Verify by clicking on " View relevant Courses " should take to relevant courses | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0539 | Competency Dashboard | Job Description | Verify by clicking on " View Courses " should display all the courses related to self assessment | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0476 | Course TOC | Module | Verify by clicking on resources should start the resources | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0477 | Course TOC | Module - SCORM | Verify by clicking on SCROM video should open it in web view | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0478 | Course TOC | Module - SCORM | Verify by clicking on " X " button should close the SCROM | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0479 | Course TOC | Module - PDF | Verify by clicking on " PDF " resources should open | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0480 | Course TOC | Module - PDF | Verify by clicking on " Full Screen " should open the resource in full screen | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0481 | Course TOC | Module - PDF | Verify by clicking on " < " and " > " icon should take user to the respective pages | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0485 | Course TOC | Module | Verify by clicking on " Next " and " Previous " icon should take user to the respective resources | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0486 | Course TOC | Module - Assessment | Veify by clicking on assessment should open the assessment | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0487 | Course TOC | Module - Assessment | Verify by clicking on " Start " should start the assessment | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0488 | Course TOC | Module - Assessment | Verify by clicking on " X " should close the assessment | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0489 | Course TOC | Module - Assessment | Verify by clicking on checkbox should select the answers | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0490 | Course TOC | Module - Assessment | Verify by clicking on back button should give pop up saying " Do you want to Exit ? " | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0491 | Course TOC | Module - Assessment | Veify by clicking on " No " should restart the assessment | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0492 | Course TOC | Module - Assessment | Verify by clicking on " Yes " Should close the pop up | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0493 | Course TOC | Module - Assessment | Verify by clicking on " Next " should move to next question | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0494 | Course TOC | Module - Assessment | Verify by clicking on " Back " should move to back question | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0496 | Course TOC | Module - Assessment | Verify by clicking on " Retake Assessment " should restart the assessment | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0497 | Course TOC | Module - Assessment | Verify by clicking on back button should give pop up saying " Do you want to Exit ? " | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0587 | Course TOC | Module - Quiz | Veify by clicking on quiz should open the quiz | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0588 | Course TOC | Module - Quiz | Verify by clicking on " Start Now " should start the quiz | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0589 | Course TOC | Module - Quiz | Verify by clicking on " X " should close the quiz | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0590 | Course TOC | Module - Quiz | Verify by clicking on checkbox should select the answers | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0591 | Course TOC | Module - Quiz | Veify by clicking on " No, Continue quiz " should restart the quiz | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0592 | Course TOC | Module - Quiz | Verify by clicking on " Yes " Should close the pop up and navigate to TOC page | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0593 | Course TOC | Module - Quiz | Verify by clicking on " Submit " should move to next question | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0594 | Course TOC | Module - Quiz | Verify by clicking on " Restart " should restart the quiz | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0596 | Course TOC | Module - Quiz | Verify by clicking on " Retake quiz " should restart the quiz | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0613 | Course TOC | Course Player - Network | Verify graceful handling of network interruption during video | High | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0216 | Create Account | Step 1 - Select Language | Verify switching back from Hindi to English works | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0233 | Create Account | Step 2 - Field Validation | Verify First Name handles empty input | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0234 | Create Account | Step 2 - Field Validation | Verify First Name handles single character | Low | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0235 | Create Account | Step 2 - Field Validation | Verify First Name handles hyphenated name | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0236 | Create Account | Step 2 - Field Validation | Verify First Name handles apostrophe in name | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0237 | Create Account | Step 2 - Field Validation | Verify First Name handles 100-character input | Low | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0239 | Create Account | Step 2 - Field Validation | Verify First Name handles special characters | Low | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0240 | Create Account | Step 2 - Field Validation | Verify Last Name handles multi-word surname | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0241 | Create Account | Step 2 - Field Validation | Verify Last Name handles HTML/script injection | High | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0255 | Create Account | Step 4 - Set Password | Verify Password field is visible and masks the input | High | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0256 | Create Account | Step 4 - Set Password | Verify eye icon toggles password visibility | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0257 | Create Account | Step 4 - Set Password | Verify Confirm Password field is visible and masks input | High | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0260 | Create Account | Step 4 - Set Password | Criterion "Minimum 8 characters" is listed | High | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0263 | Create Account | Step 4 - Set Password | Criterion "One special character" is listed | High | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0264 | Create Account | Step 4 - Set Password | Verify all 4 criteria turn green when strong password is entered | High | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0268 | Create Account | Step 4 - Set Password | Verify password without special character fails the special-char criterion | High | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0270 | Create Account | Step 4 - Set Password | Verify matching passwords are accepted | High | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0271 | Create Account | Step 4 - Set Password | Verify mismatched passwords show an error | High | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0273 | Create Account | Step 4 - Set Password | Verify Next button is enabled with matching valid passwords | High | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0274 | Create Account | Step 4 - Set Password | Verify Next button submits and creates the account | High | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0394 | Home (Authenticated) | Session / Auth | Verify accessing /page/home without login redirects to /public/login | Critical | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0396 | Home (Authenticated) | Session / Auth | Verify session persists across page reloads | High | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0446 | Home (Authenticated) | Home (Authenticated) | Verify by clicking on get help icon | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0450 | Home (Authenticated) | Home (Authenticated) | Verify by clicking on any courses should open " Tell us more about you " page for 1st time | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0453 | Home (Authenticated) | Home (Authenticated) | Verify if " Next " button is clickable or not | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0454 | Home (Authenticated) | Home (Authenticated) | Verify if user can select the background of their choice | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0455 | Home (Authenticated) | Home (Authenticated) | Verify if all the blocks are clickable or not | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0456 | Home (Authenticated) | Home (Authenticated) | Verify by clicking on respective blocks is opening respective details about background | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0457 | Home (Authenticated) | Home (Authenticated) | Verify by clicking on change is landing user to the background blocks page | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0459 | Home (Authenticated) | Home (Authenticated) | Verify cliking on done should take user to the course which clicked before | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0460 | Home (Authenticated) | Home (Authenticated) | Verify by clicking on any courses should open TOC page | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0461 | Home (Authenticated) | Home (Authenticated) | Verify by clicking on " View all course " Should display all courses | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0462 | Home (Authenticated) | Home (Authenticated) | Verify by clicking on youtube icon in " How does it work " | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0465 | Home (Authenticated) | Home (Authenticated) | Verify by clicking on " Get certified " field | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0619 | Home (Authenticated) | Adhoc - Browser Back | Verify browser back button navigation works correctly | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0286 | Login | Header | Verify Back arrow button is visible and clickable | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0287 | Login | Header | Verify Help button opens the chat support modal | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0290 | Login | Login Mode Toggle | Verify "Login with OTP" radio is visible and selected by default | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0291 | Login | Login Mode Toggle | Verify "Login with Password" radio switches to password mode | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0292 | Login | Login Mode Toggle | Verify toggling back to OTP hides the password field | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0293 | Login | OTP Login Flow | Verify identifier field accepts a valid phone number | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0294 | Login | OTP Login Flow | Verify identifier field accepts a valid email address | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0295 | Login | OTP Login Flow | Verify "Get OTP" button is visible | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0296 | Login | OTP Login Flow | "Get OTP" button is disabled when input is empty | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0297 | Login | OTP Login Flow | "Get OTP" button is clickable with valid input | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0298 | Login | Password Login Flow | Verify identifier field is visible in password mode | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0299 | Login | Password Login Flow | Verify password field is visible and masks input | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0300 | Login | Password Login Flow | Verify eye icon toggles password visibility | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0301 | Login | Password Login Flow | "Forgot Password?" link is visible and clickable | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0302 | Login | Password Login Flow | "Login" button submits credentials | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0304 | Login | Create Account | "Create an Account" button is visible and navigates to signup | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0305 | Login | Help Chat Support Modal | Modal heading "Aastrika Sphere chat support" is displayed | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0306 | Login | Help Chat Support Modal | "Chat with us on WhatsApp" button opens WhatsApp | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0307 | Login | Help Chat Support Modal | "Chat with us" button opens in-app chat | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0308 | Login | Help Chat Support Modal | Modal close (×) button dismisses the modal | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0309 | Login | Input Validation Edge Cases | Identifier field handles empty input | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0310 | Login | Input Validation Edge Cases | Identifier field handles whitespace-only input | Low | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0311 | Login | Input Validation Edge Cases | Identifier field handles a single character | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0312 | Login | Input Validation Edge Cases | Identifier field handles 10-digit phone | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0313 | Login | Input Validation Edge Cases | Identifier field handles phone with country code | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0314 | Login | Input Validation Edge Cases | Identifier field handles a standard email address | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0315 | Login | Input Validation Edge Cases | Identifier field handles uppercase email | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0316 | Login | Input Validation Edge Cases | Identifier field handles special characters only | Low | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0317 | Login | Input Validation Edge Cases | Identifier field handles very long input (256 chars) | Low | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0318 | Login | Input Validation Edge Cases | Identifier field is safe against XSS payload | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0322 | Login | Page Health | No console errors are thrown on page load | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0414 | Login | Login | Verify by clicking on login button should open login page | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0415 | Login | Login | Verify by clicking on " X " icon is closing the page | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0416 | Login | Login | Verify if the radio buttons of login with OTP and Login with password is working or not | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0417 | Login | Login | Verify by giving wrong email address in login with OTP | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0418 | Login | Login | Verfy by clicking on " Get OTP " without filling email/password | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0419 | Login | Login | Verify login with valid email and password | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0420 | Login | Login | Verify login with valid email and invalid password | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0421 | Login | Login | Verify login with invalid email and invalid password | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0422 | Login | Login | Verify clicking on sign in with out filling email and password | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0423 | Login | Login | Verify by clicking on create account button in login page | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0424 | Login | Login | Verify by clicking on " Get help on whatsapp " | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0425 | Login | Login | Verify by clicking on Get OTP should land on OTP page | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0426 | Login | Login | Verify by cliking on " Submit " should land on T&C page | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0427 | Login | Login | Verify by clicking on " resend OTP " should resend the OTP | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0428 | Login | Login | Verify by clicking on " Get help on whatsapp " | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0429 | Login | Login | Verify by clicking on " Back to aastrika sphere " | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0602 | Login | Login - Negative | Verify login fails with invalid email format | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0603 | Login | Login - Negative | Verify login fails with empty credentials | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0604 | Login | Login - Negative | Verify login fails with wrong OTP (phone-based) | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0605 | Login | Login - Negative | Verify multiple failed login attempts trigger appropriate handling | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0606 | Login | Login - Ad-hoc | Verify rapid clicking of Login button does not submit multiple times | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0607 | Login | Login - Session | Verify session expiry redirects to login | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0505 | My Courses | Completed | Verify by clicking on " Certificate " Should start downloading the certificate | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0598 | Notifications | Notifications | Verify clicking on notification icon when no notification is received | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0599 | Notifications | Notifications | Verify clicking on notification icon when notification is received | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0600 | Notifications | Notifications | Verify clicking on any one received notification | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0601 | Notifications | Notifications | Verify clicking on mark all as read button when notifications are present | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0617 | Notifications | Notifications - Empty | Verify empty state for new users with no notifications | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0618 | Notifications | Notifications - Badge | Verify unread count badge updates after reading notifications | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0004 | Public Page | Header | Verify login modal can be closed | High | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0014 | Public Page | Hero Banner | Verify carousel auto-rotates or responds to dot click | Low | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0402 | Public Page | Public Page | Verify by clicking on " Read Chapter " button | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0403 | Public Page | Public Page | Verify by clicking on device back button when in RMC chapter | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0404 | Public Page | Public Page | Verify by clicking on youtube icon in " How does it work " | Medium | ✔ Done | ➕ To Add | Tier 2 — no clear automation match (review)
TC-0540 | Search | Search | Verify by clicking on " Search Bar " should display recently published courses | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0541 | Search | Search | Verify by clicking on " Search Bar " should display all the courses | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0542 | Search | Search | Verify if the selected language is selected as english | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0543 | Search | Search | Verify by clicking on search icon should refresh the page | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0544 | Search | Search | Verify by clicking on search field should user able to enter the items | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0545 | Search | Search | Verify by entering the field in Hindi language should display list of Hindi courses related to the term | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0546 | Search | Search | Verify by clicking on select langugae should be able to select the language | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0547 | Search | Search | Verify by clicking on aastrika logo Should take user to the home page | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0614 | Search | Search - Negative | Verify search with empty query shows guidance or no results | Low | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0615 | Search | Search - Negative | Verify search for nonexistent term shows empty state | Medium | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0616 | Search | Search - Edge | Verify search handles special characters safely | High | ✔ Done | ➕ To Add | Tier 1 — confirmed gap (no automation module)
TC-0185 | Account | Language Preference | Verify Select Hindi, Save, and persistence after reload | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0186 | Account | Language Preference | Verify Switch back to English, Save, and persistence | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0207 | Account | Header & Page Health | Verify unauthenticated access redirects to login | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0550 | Account | Account | Verify by clicking on back button Should take user to the home page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0553 | Account | Profile Picture | Verify by clicking on " Add your own Image " should use user to select his own image | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0554 | Account | Language Preference | Verify by clicking on " Language Preferance " should open new tab to select the language | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0555 | Account | Language Preference | Verify by clicking on both the radio buttons and save the button | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0556 | Account | Language Preference | Verify by clicking on back button Should take user to the account page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0557 | Account | Language Preference | Verify by clicking on save button should take user to the home page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0558 | Account | Language Preference | Verify by clicking on the Hindi language should translate all the words to Hindi | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0559 | Account | My Certificates | Verify by clicking on " My certificates " should display all the completed certificates | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0561 | Account | Profile Details | Verify by clicking on " Profile Details " should display all the details related to profile | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0562 | Account | Profile Details | Verify by clicking on edit icon in personal details should open edit tab | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0563 | Account | Profile Details | Verify by clicking on DOB field should be able to change | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0568 | Account | Profile Details | Verify by clicking on " Phone number " should be able to edit | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0570 | Account | Profile Details | Verfiy by clicking on " Pincode " should be able to edit | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0571 | Account | Profile Details | Verify after entering any field " Save " Button should be enabled | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0572 | Account | Organization Details | Verify by clicking on " Organization Details " Should display all the details about organization | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0573 | Account | Organization Details | Verify by clicking on edit icon in organization details should open edit tab in new page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0574 | Account | Organization Details | Verify by clicking on " Desigation " drop down should be able to select | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0575 | Account | Organization Details | Verify after entering any field " Save " Button should be enabled | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0576 | Account | Academic Details | Verify by clicking on " Academic Details " should open new tab | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0577 | Account | Academic Details | Verify by clicking on " + " to add the academic details | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0578 | Account | Academic Details | Verify by clicking on " Grade/Degree " drop down should be able to select | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0579 | Account | Academic Details | Verify by clicking on " Institution Name " field should be able to edit | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0580 | Account | Academic Details | Verify by clicking on " Year of passing " field should be able to edit | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0581 | Account | Academic Details | Verify if save button is enabled only when given valid details | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0582 | Account | Academic Details | Verify by clicking on back button Should take user to the account page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0508 | Competency Dashboard | Required | Verify by clicking on " Required " should display all the self assessment list | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0509 | Competency Dashboard | Required | Verify by clicking on " assess " should Open Pop up for the self assessment | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0510 | Competency Dashboard | Required | Verify By clicking on " Start Now " should start the self assessment | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0511 | Competency Dashboard | Required | Verify by clicking on " X " should close the Self Assessment | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0512 | Competency Dashboard | Required | Verify by clicking on checkbox should select the answers | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0513 | Competency Dashboard | Required | Verify by clicking on back button should give pop up saying " Do you want to Exit ? " | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0514 | Competency Dashboard | Required | Veify by clicking on " No " should restart the assessment | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0515 | Competency Dashboard | Required | Verify by clicking on " Yes " Should close the pop up | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0516 | Competency Dashboard | Required | Verify by clicking on " Next " should move to next question | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0517 | Competency Dashboard | Required | Verify by clicking on " Back " should move to back question | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0520 | Competency Dashboard | Required | Verify by clicking on " Go to Competency Dashboard " should take to passbook page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0521 | Competency Dashboard | Required | Verify by clicking on " View Courses " should display all the courses related to self assessment | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0522 | Competency Dashboard | Passbook | Verify by clicking on dropdown button should display the completed self assessment in passbook | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0523 | Competency Dashboard | Passbook | Verify by clicking on levels should display the completed self assessment in passbook | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0524 | Competency Dashboard | Job Description | Verify by clicking on " Job Description " should display all the Roles courses | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0525 | Competency Dashboard | Job Description | Verify by clicking on dropdown button should display the " activities " and " competency " in the roles | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0526 | Competency Dashboard | Job Description | Verify by clicking on dropdown button in competencies should display all the levels | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0527 | Competency Dashboard | Job Description | Verify by clicking on " assess " should Open Pop up for the self assessment | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0528 | Competency Dashboard | Job Description | Verify By clicking on " Start Now " should start the self assessment | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0529 | Competency Dashboard | Job Description | Verify by clicking on " X " should close the Self Assessment | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0530 | Competency Dashboard | Job Description | Verify by clicking on checkbox should select the answers | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0531 | Competency Dashboard | Job Description | Verify by clicking on back button should give pop up saying " Do you want to Exit ? " | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0532 | Competency Dashboard | Job Description | Veify by clicking on " No " should restart the assessment | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0533 | Competency Dashboard | Job Description | Verify by clicking on " Yes " Should close the pop up | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0534 | Competency Dashboard | Job Description | Verify by clicking on " Next " should move to next question | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0535 | Competency Dashboard | Job Description | Verify by clicking on " Back " should move to back question | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0538 | Competency Dashboard | Job Description | Verify by clicking on " Go to Competency Dashboard " should take to passbook page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0467 | Course TOC | Course TOC | Verify by cliking on application back icon is taking user to the homepage | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0468 | Course TOC | Course TOC | Verify by clicking on Org should land in organization page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0469 | Course TOC | Course TOC | Verify by clicking on details shlould display the course details in popup | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0470 | Course TOC | Course TOC | Verify by clicking on " X " button should close the details popup | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0471 | Course TOC | Course TOC | Verify by clicking on " Certificate " button should give popup saying to complete the course | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0472 | Course TOC | Course TOC | Verify by clicking on " Close " button should close the popup | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0473 | Course TOC | Course TOC | Verify by clicking on " Share " button | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0474 | Course TOC | Course TOC | Verify by clicking on " Start " should start the course | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0475 | Course TOC | Overview | Verify by clicking on " License Terms " link | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0612 | Course TOC | Course Player - Resilience | Verify course progress is preserved if app force-closed mid-video | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0209 | Create Account | Step 1 - Select Language | Verify "Select Language" heading is visible | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0210 | Create Account | Step 1 - Select Language | Verify no language is pre-selected on first page load | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0212 | Create Account | Step 1 - Select Language | Verify English radio is visible and selectable via radio button click | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0213 | Create Account | Step 1 - Select Language | Verify English can be selected by clicking the "English" text label | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0217 | Create Account | Step 1 - Select Language | Verify Next button enables after a language is selected | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0218 | Create Account | Step 1 - Select Language | Verify Next button navigates to Create Your Account form after selecting English | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0219 | Create Account | Step 1 - Select Language | Verify Next button works when Hindi is selected | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0221 | Create Account | Step 2 - Create Account Form | Verify "Start by entering your details" sub-heading is visible | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0222 | Create Account | Step 2 - Create Account Form | Verify First Name field is visible and accepts input | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0223 | Create Account | Step 2 - Create Account Form | Verify Last Name field is visible and accepts input | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0226 | Create Account | Step 2 - Create Account Form | Verify "Choose your Login method" heading is visible | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0227 | Create Account | Step 2 - Create Account Form | "By OTP" radio option is visible and selectable | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0228 | Create Account | Step 2 - Create Account Form | "By password" radio option is visible and selectable | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0229 | Create Account | Step 2 - Create Account Form | Verify selecting one login method unselects the other | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0230 | Create Account | Step 2 - Create Account Form | Verify Next button is disabled when required fields are empty | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0231 | Create Account | Step 2 - Create Account Form | Verify Next button enables with all required fields filled | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0232 | Create Account | Step 2 - Create Account Form | Verify Next button click opens Name Confirmation modal | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0238 | Create Account | Step 2 - Field Validation | Verify First Name handles numeric input | Low | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0242 | Create Account | Step 2 - Field Validation | Verify Email field rejects email without @ symbol | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0243 | Create Account | Step 2 - Field Validation | Verify Email field rejects email without domain TLD | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0244 | Create Account | Step 2 - Field Validation | Verify Email field rejects email without local part | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0245 | Create Account | Step 2 - Field Validation | Verify Email field rejects email with spaces in local part | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0251 | Create Account | Step 3 - Name Confirmation Modal | "Confirm name" button is visible and advances to password screen | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0272 | Create Account | Step 4 - Set Password | Verify Next button is disabled with empty password fields | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0280 | Create Account | Page Health | No console errors during Create Account flow | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0281 | Create Account | Page Health | Verify back-navigation in browser does not break the flow | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0282 | Create Account | Page Health | Verify page reload mid-flow handles state gracefully | Low | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0283 | Create Account | Page Health | Verify duplicate-email registration shows appropriate error | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0284 | Create Account | Page Health | Verify successful account creation reaches the post-signup destination | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0432 | Create Account | Create Account | Verify if the application back button is taking user to the public page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0433 | Create Account | Create Account | Verfiy if clicking on aastrika logo is taking user to the public page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0434 | Create Account | Create Account | Verify if both radio buttons are working to select the language | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0435 | Create Account | Create Account | Verify when clicking on Hindi all the Info is translating to Hindi language | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0436 | Create Account | Create Account | Verify if save button is clickable or not | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0438 | Create Account | Create Account | Verify filling up all valid details in create account page and click on next button | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0439 | Create Account | Create Account | Verify filling up all wtih Invalid email id in signup page and click on next button | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0441 | Create Account | Create Account | Verify if clicking on application back button is landing to language selection page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0442 | Create Account | Create Account | Verify by entering the right OTP and click on next | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0443 | Create Account | Create Account | Verify by clicking on " Click here " to resend the OTP to registerd email/mobile number | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0444 | Create Account | Create Account | Verify if the wrong OTP enters should give correct toast | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0608 | Create Account | Create Account - Negative | Verify signup fails with already-registered email | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0609 | Create Account | Create Account - Negative | Verify signup fails with weak password | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0610 | Create Account | Create Account - Negative | Verify mismatched password confirmation is blocked | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0611 | Create Account | Create Account - Negative | Verify Terms checkbox required for signup | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0326 | Home (Authenticated) | Header | Verify search bar is visible with placeholder | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0328 | Home (Authenticated) | Header | Verify search submission with Enter key triggers results | Critical | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0332 | Home (Authenticated) | Header | Verify "Home" nav link is present and active | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0333 | Home (Authenticated) | Header | Verify "My Courses" nav link navigates correctly | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0334 | Home (Authenticated) | Header | Verify "Competency" nav link navigates correctly | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0335 | Home (Authenticated) | Header | Verify "Account" nav link opens the Account section | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0342 | Home (Authenticated) | Welcome / Hero | Verify "Watch how Sphere works" headline is visible in carousel | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0345 | Home (Authenticated) | Welcome / Hero | Verify clicking a pagination dot switches the carousel slide | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0349 | Home (Authenticated) | Continue Learning | Verify clicking a Continue Learning card opens the course | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0366 | Home (Authenticated) | Info Cards | Verify clicking "Register for a course" card triggers navigation | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0367 | Home (Authenticated) | Info Cards | Verify clicking "Take the course" card triggers navigation | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0368 | Home (Authenticated) | Info Cards | Verify clicking "Get certified" card triggers navigation | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0375 | Home (Authenticated) | Footer - Help & Contact | Verify support email click opens mail client | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0445 | Home (Authenticated) | Home (Authenticated) | Verify by clicking on aastrika logo should refresh the page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0448 | Home (Authenticated) | Home (Authenticated) | Verify by clicking on " X " button user should land in private home page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0449 | Home (Authenticated) | Home (Authenticated) | Verify by clicking on " Watch tutorials on how sphere works " | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0463 | Home (Authenticated) | Home (Authenticated) | Verify by clicking on " Register for a course " field | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0464 | Home (Authenticated) | Home (Authenticated) | Verify by clicking on " Take the course " field | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0289 | Login | Welcome Section | Verify sub-heading "Login with your Aastrika account" is displayed | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0584 | Logout | Logout | Verify by clicking on " Logout " button pop up should be displayed to make sure | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0585 | Logout | Logout | Verify by clicking on " No " should stay in the account page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0586 | Logout | Logout | Verify by clciking on " Yes " should naviagte to public home page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0096 | My Courses | Page Heading & Tabs | Verify "Started" tab is selected by default | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0102 | My Courses | Started Tab | Verify progress percentage text is displayed | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0126 | My Courses | Tab Switching | Verify URL stays on /my_courses across all tab switches | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0128 | My Courses | Header | Verify search bar is visible on My Courses | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0133 | My Courses | Page Quality | Verify My Courses loads without console errors | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0138 | My Courses | Page Quality | Verify URL persists on page reload | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0139 | My Courses | Page Quality | Verify unauthenticated access to My Courses redirects to login | Critical | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0499 | My Courses | My Courses | Verify by clicking on " My course " should highlight in nav bar | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0500 | My Courses | My Courses | Verify by clicking on " My course " should open the new tab | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0504 | My Courses | Completed | Verify by clicking on Completed course should display " Start Again " in TOC page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0002 | Public Page | Header | Verify Log In button is visible in header | Critical | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0003 | Public Page | Header | Verify Log In button is clickable and opens login modal | Critical | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0008 | Public Page | Hero Banner | Verify Create Account button is visible and enabled | Critical | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0009 | Public Page | Hero Banner | Verify Create Account button navigates to registration page | Critical | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0013 | Public Page | Hero Banner | Verify carousel dot 2 is clickable and changes slide | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0022 | Public Page | Top Courses | Verify 'View All' in Top Courses is clickable | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0026 | Public Page | Top Courses | Verify clicking a course card navigates to course detail page | Critical | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0049 | Public Page | How Sphere Works | Verify Step 1 play button is clickable | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0051 | Public Page | How Sphere Works | Verify Step 2 play button is clickable | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0053 | Public Page | How Sphere Works | Verify Step 3 play button is clickable | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0056 | Public Page | Transform CTA | Verify 'Start Today' button is enabled | Critical | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0057 | Public Page | Transform CTA | Verify 'Start Today' button navigates to Create Account page | Critical | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0067 | Public Page | Footer - Quick Links | Verify 'Terms of Use' link is clickable and navigates to terms page | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0075 | Public Page | Footer - Additional Links | Verify Aastrika Foundation link is clickable and opens correct URL | High | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0077 | Public Page | Footer - Social Icons | Verify Twitter/X icon has valid href and is clickable | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0079 | Public Page | Footer - Social Icons | Verify Facebook icon has valid href and is clickable | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0081 | Public Page | Footer - Social Icons | Verify Instagram icon has valid href and is clickable | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0083 | Public Page | Footer - Social Icons | Verify LinkedIn icon has valid href and is clickable | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0397 | Public Page | Public Page | Verify clicking on login button | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0398 | Public Page | Public Page | Verify clicking on create account button | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0399 | Public Page | Public Page | Verify by clicking on " Watch tutorials on how sphere works " | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0400 | Public Page | Public Page | Verify by clicking on courses in the public page | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0401 | Public Page | Public Page | Verify by clicking on " Start now " button | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0405 | Public Page | Public Page | Verify by clicking on " Register for a course " field | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0406 | Public Page | Public Page | Verify by clicking on " Take the course " field | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0407 | Public Page | Public Page | Verify by clicking on " Get certified " field | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0409 | Public Page | Public Page | Verify by clicking on " Privacy Policy " | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0410 | Public Page | Public Page | Verify by clicking on " Terms of use " | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0412 | Public Page | Public Page | Verify by clicking on " Talk to us on Whatsapp " | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0413 | Public Page | Public Page | Verify by clicking on " Additional links " | Medium | ✔ Done | ◐ Confirm | Functional — manual done; confirm if already automated
TC-0140 | Account | Landing & Left Nav | Verify URL contains "/profile" (or account path) | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0141 | Account | Landing & Left Nav | Verify user name is visible in left panel | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0144 | Account | Landing & Left Nav | Verify pencil edit icon on profile picture is visible | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0145 | Account | Landing & Left Nav | Verify "Personal Details" nav link is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0146 | Account | Landing & Left Nav | Verify "Organization Details" nav link is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0147 | Account | Landing & Left Nav | Verify "Academic Details" nav link is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0148 | Account | Landing & Left Nav | Verify "Language Preference" nav link is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0149 | Account | Landing & Left Nav | Verify "My Certificates" nav link is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0151 | Account | Landing & Left Nav | Verify "Logout" button is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0152 | Account | Landing & Left Nav | Verify "Personal Details" is active by default on first load | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0153 | Account | Personal Details | Verify "Personal Details" page heading is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0154 | Account | Personal Details | Verify First Name field is visible with value | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0155 | Account | Personal Details | Verify Last Name field is visible with value | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0156 | Account | Personal Details | Verify Phone Number field is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0157 | Account | Personal Details | Verify Email ID field is visible and masked | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0158 | Account | Personal Details | Verify Date of Birth section is visible with Year/Month/Date dropdowns | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0159 | Account | Personal Details | Verify Country dropdown is visible | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0161 | Account | Personal Details | Verify Save button is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0162 | Account | Personal Details | Verify Fill Phone Number and Pincode then Save works | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0163 | Account | Personal Details | Verify saved values persist after page reload | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0164 | Account | Personal Details | Verify DOB Year dropdown can be changed | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0165 | Account | Personal Details | Verify Country dropdown can be changed | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0166 | Account | Organization Details | Verify "Organizational Details" page heading is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0167 | Account | Organization Details | Verify "Background" label is visible | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0168 | Account | Organization Details | Verify Background dropdown shows current value | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0169 | Account | Organization Details | Verify Designation dropdown is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0171 | Account | Organization Details | Verify Organization type / Private Sector dropdown is visible | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0172 | Account | Organization Details | Verify Organization Name input is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0173 | Account | Organization Details | Verify Save button is visible on Organization Details | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0174 | Account | Organization Details | Verify Fill Organization Name and Save works | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0175 | Account | Organization Details | Verify saved Organization Name persists after reload | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0177 | Account | Academic Details | Verify "+ Add Education" link is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0178 | Account | Academic Details | Verify clicking "+ Add Education" opens entry form or modal | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0179 | Account | Academic Details | Verify "Academic Details" is highlighted as active in left nav | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0180 | Account | Language Preference | Verify "Language Preference" page heading is visible | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0181 | Account | Language Preference | Verify English radio option is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0182 | Account | Language Preference | Verify Hindi radio option (हिंदी) is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0183 | Account | Language Preference | Verify English is selected by default | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0184 | Account | Language Preference | Verify Save button is visible on Language Preference | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0187 | Account | My Certificates | Verify "My Certificates" is active in left nav | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0188 | Account | My Certificates | Verify empty state "No Certificates" is visible for new users | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0189 | Account | My Certificates | Verify no certificate cards are rendered when user has none | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0190 | Account | Profile Picture | Verify clicking the pencil icon opens an upload/edit option | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0191 | Account | Help and Support | Verify clicking "Help and Support" navigates or opens helper | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0192 | Account | Logout Flow | Verify clicking Logout opens confirmation modal | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0193 | Account | Logout Flow | Verify Logout modal shows "Are you sure?" text | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0194 | Account | Logout Flow | Verify Logout modal has "Yes" and "No" buttons | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0195 | Account | Logout Flow | Verify clicking "No" closes modal and keeps user signed in | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0197 | Account | Header & Page Health | Verify search bar is visible on Account page | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0198 | Account | Header & Page Health | Verify "Account" nav link is marked active | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0199 | Account | Header & Page Health | Verify clicking "Home" navigates to Home page | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0200 | Account | Header & Page Health | Verify dark mode toggle is visible on Account | Low | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0202 | Account | Header & Page Health | Verify no console errors on Account page load | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0203 | Account | Header & Page Health | Verify page renders on mobile (390 × 844) | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0204 | Account | Header & Page Health | Verify page renders on tablet (768 × 1024) | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0205 | Account | Header & Page Health | Verify page renders on desktop (1440 × 900) | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0206 | Account | Header & Page Health | Verify URL persists on reload | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0551 | Account | Profile Picture | Verify by clicking on edit icon in profile pic should open the pop up for different images | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0552 | Account | Profile Picture | Verify by clicking on " X " should close the profile picture | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0506 | Competency Dashboard | Competency Dashboard | Verify by clicking on " Competency " should highlight in nav bar | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0507 | Competency Dashboard | Passbook | Verify by clicking on " Competency " should open the tab with passbook | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0208 | Create Account | Step 1 - Select Language | Verify Aastrika Sphere logo is visible on language page | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0211 | Create Account | Step 1 - Select Language | Verify Next button is disabled until a language is selected | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0214 | Create Account | Step 1 - Select Language | Verify Hindi (हिंदी) radio option is visible and selectable | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0215 | Create Account | Step 1 - Select Language | Verify selecting Hindi unselects English (single-choice behavior) | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0220 | Create Account | Step 2 - Create Account Form | Verify "Create your account" heading is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0224 | Create Account | Step 2 - Create Account Form | Verify Phone/Email field accepts a valid email address | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0225 | Create Account | Step 2 - Create Account Form | Verify Phone/Email field accepts a valid phone number | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0246 | Create Account | Step 2 - Field Validation | Verify Email field accepts a valid email | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0275 | Create Account | Responsive Layout | Create Account form renders correctly on mobile (390 × 844) | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0277 | Create Account | Responsive Layout | Create Account form renders correctly on desktop (1440 × 900) | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0430 | Create Account | Create Account | Verify by clicking on create account button | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0437 | Create Account | Create Account | Verify by clicking on create account button | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0324 | Home (Authenticated) | Header | Verify Aastrika Sphere logo is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0325 | Home (Authenticated) | Header | Verify logo click navigates to Home page | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0327 | Home (Authenticated) | Header | Verify search bar accepts text input | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0329 | Home (Authenticated) | Header | Verify search icon is visible inside the search bar | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0330 | Home (Authenticated) | Header | Verify dark mode toggle is visible in header | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0331 | Home (Authenticated) | Header | Verify dark mode toggle switches the theme | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0337 | Home (Authenticated) | Notifications | Verify notification bell click opens notifications panel | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0338 | Home (Authenticated) | Welcome / Hero | Verify "Welcome !" greeting is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0339 | Home (Authenticated) | Welcome / Hero | Verify user's display name is shown below "Welcome !" | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0340 | Home (Authenticated) | Welcome / Hero | Verify "Start Learning" subtitle is visible | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0341 | Home (Authenticated) | Welcome / Hero | Verify hero carousel banner is visible on the right | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0343 | Home (Authenticated) | Welcome / Hero | Verify "Watch now" button is visible and clickable | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0346 | Home (Authenticated) | Continue Learning | Verify "CONTINUE LEARNING" section heading is visible (if user has in-progress courses) | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0347 | Home (Authenticated) | Continue Learning | Verify Continue Learning section is hidden for new users | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0348 | Home (Authenticated) | Continue Learning | Verify "View All" link is visible next to Continue Learning heading | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0350 | Home (Authenticated) | CNE Courses | Verify "CNE COURSES" section heading is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0351 | Home (Authenticated) | CNE Courses | Verify "View All" link is visible for CNE Courses | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0352 | Home (Authenticated) | CNE Courses | Verify CNE Courses section displays at least 4 course cards | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0353 | Home (Authenticated) | CNE Courses | Verify each CNE card displays course title | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0354 | Home (Authenticated) | CNE Courses | Verify CNE points badge is displayed on each card | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0357 | Home (Authenticated) | CNE Courses | Verify clicking a CNE card opens the course detail page | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0358 | Home (Authenticated) | CNE Courses | Verify "View All" CNE click navigates to all CNE courses | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0371 | Home (Authenticated) | Footer - Quick Links | Verify "Privacy policy" link is visible and clickable | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0372 | Home (Authenticated) | Footer - Quick Links | Verify "Terms of Use" link is visible and clickable | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0374 | Home (Authenticated) | Footer - Help & Contact | Verify support email link is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0377 | Home (Authenticated) | Footer - Help & Contact | Verify WhatsApp button opens WhatsApp chat | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0379 | Home (Authenticated) | Footer - Additional Links | Verify Aastrika Foundation link is visible with URL | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0380 | Home (Authenticated) | Footer - Additional Links | Verify Aastrika Foundation link opens in new tab | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0388 | Home (Authenticated) | Page Quality | Verify no JavaScript console errors on page load | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0389 | Home (Authenticated) | Page Quality | Verify page renders correctly on mobile viewport (390 × 844) | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0390 | Home (Authenticated) | Page Quality | Verify page renders correctly on tablet viewport (768 × 1024) | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0391 | Home (Authenticated) | Page Quality | Verify page renders correctly on desktop viewport (1440 × 900) | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0392 | Home (Authenticated) | Page Quality | Verify header stays sticky / fixed on scroll | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0285 | Login | Header | Verify Aastrika Sphere logo is displayed | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0319 | Login | Responsive Layout | Page renders correctly on mobile viewport (390 × 844) | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0320 | Login | Responsive Layout | Page renders correctly on tablet viewport (768 × 1024) | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0321 | Login | Responsive Layout | Page renders correctly on desktop viewport (1440 × 900) | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0583 | Logout | Logout | Verify by clicking on " Logout " button is clickable or not | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0091 | My Courses | Page Heading & Tabs | Verify "My Courses" page heading is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0092 | My Courses | Page Heading & Tabs | Verify URL contains "/my_courses" | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0093 | My Courses | Page Heading & Tabs | Verify "Started" tab is visible with course count | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0095 | My Courses | Page Heading & Tabs | Verify "Completed" tab is visible with course count | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0098 | My Courses | Started Tab | Verify Started tab content is displayed when tab is active | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0099 | My Courses | Started Tab | Verify each Started course displays a thumbnail image | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0100 | My Courses | Started Tab | Verify each Started course displays its title | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0101 | My Courses | Started Tab | Verify progress bar is visible on each Started course | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0103 | My Courses | Started Tab | Verify "Resume" button is visible on each Started course | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0104 | My Courses | Started Tab | Verify clicking "Resume" navigates to the course player | Critical | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0105 | My Courses | Started Tab | Verify clicking the course title navigates to the course | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0106 | My Courses | Started Tab | Verify Started tab count matches the actual number of visible course rows | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0107 | My Courses | For You Tab | Verify For You tab content is displayed when tab is active | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0108 | My Courses | For You Tab | Verify For You section displays course cards in a grid layout | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0109 | My Courses | For You Tab | Verify each For You card displays a thumbnail image | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0110 | My Courses | For You Tab | Verify "Certificate" badge is visible on each card (top-left) | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0113 | My Courses | For You Tab | Verify course titles are visible on each card | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0114 | My Courses | For You Tab | Verify clicking a For You card opens the course detail page | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0115 | My Courses | For You Tab | Verify For You tab count matches displayed card count | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0117 | My Courses | Completed Tab | Verify Completed tab becomes active when clicked | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0118 | My Courses | Completed Tab | Verify Completed tab count is 0 for a new user | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0119 | My Courses | Completed Tab | Verify empty-state message is visible when no courses are completed | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0120 | My Courses | Completed Tab | Verify empty-state message exact text matches | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0121 | My Courses | Completed Tab | Verify no course cards are visible when Completed tab is empty | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0122 | My Courses | Completed Tab | Verify no "Resume" buttons appear in the Completed tab | Low | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0123 | My Courses | Tab Switching | Verify Started → For You switch displays different content | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0124 | My Courses | Tab Switching | Verify For You → Completed switch shows empty state | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0125 | My Courses | Tab Switching | Verify Completed → Started switch restores Started content | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0129 | My Courses | Header | Verify "My Courses" nav link is marked as active | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0130 | My Courses | Header | Verify clicking "Home" from My Courses navigates to Home page | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0131 | My Courses | Header | Verify dark mode toggle is visible on My Courses | Low | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0134 | My Courses | Page Quality | Verify My Courses renders correctly on mobile viewport (390 × 844) | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0136 | My Courses | Page Quality | Verify My Courses renders correctly on desktop viewport (1440 × 900) | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0501 | My Courses | Started | Verify that the started courses should display in the started courses | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0503 | My Courses | Completed | Verify that the completed courses should display under " Completed " tab | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0001 | Public Page | Header | Verify Aastrika Sphere logo is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0005 | Public Page | Hero Banner | Verify 'Access free Healthcare courses' heading is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0010 | Public Page | Hero Banner | Verify CNE Hours banner text is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0011 | Public Page | Hero Banner | Verify 'View courses' button in CNE banner is clickable | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0015 | Public Page | Stats Row | Verify '310,000+ Learners onboarded' stat is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0016 | Public Page | Stats Row | Verify '490+ Number of courses' stat is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0017 | Public Page | Stats Row | Verify '57.5 CNE Hours' stat is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0018 | Public Page | Stats Row | Verify '400,000+ Total certificate issued' stat is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0020 | Public Page | Top Courses | Verify 'TOP COURSES' section heading is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0021 | Public Page | Top Courses | Verify 'View All' link in Top Courses is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0028 | Public Page | CNE Courses | Verify 'CNE COURSES' section heading is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0029 | Public Page | CNE Courses | Verify 'View All' link in CNE Courses is visible and clickable | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0030 | Public Page | CNE Courses | Verify CNE course cards are displayed | Critical | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0034 | Public Page | CNE Courses | Verify 'Normal Labour & Birth and AMTSL' card is visible and clickable | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0035 | Public Page | CNE Courses | Verify 'Integrated Sexual and Reproductive Health (ISRH)' card is visible and clickable | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0037 | Public Page | CNE Courses | Verify carousel right-arrow button is visible and clickable | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0038 | Public Page | Trusted By | Verify 'Trusted By' heading is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0046 | Public Page | How Sphere Works | Verify 'How Sphere works' heading is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0048 | Public Page | How Sphere Works | Verify Step 1 — 'Register for a course' card is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0050 | Public Page | How Sphere Works | Verify Step 2 — 'Take the course' card is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0052 | Public Page | How Sphere Works | Verify Step 3 — 'Get certified' card is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0054 | Public Page | Transform CTA | Verify 'Transform your Healthcare career through Sphere!' text is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0055 | Public Page | Transform CTA | Verify 'Start Today' button is visible | Critical | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0063 | Public Page | Footer - Quick Links | Verify 'Quick Links' heading in footer is visible | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0064 | Public Page | Footer - Quick Links | Verify 'Privacy policy' link is visible in footer | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0065 | Public Page | Footer - Quick Links | Verify 'Privacy policy' link is clickable and navigates to policy page | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0066 | Public Page | Footer - Quick Links | Verify 'Terms of Use' link is visible in footer | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0069 | Public Page | Footer - Help & Contact | Verify 'support@aastrika.org' email link is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0071 | Public Page | Footer - Help & Contact | Verify 'Talk to us on WhatsApp' button is visible | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0085 | Public Page | Page Quality | Verify no broken images exist on the full public page | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0086 | Public Page | Page Quality | Verify no console errors on page load | High | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0088 | Public Page | Page Quality | Verify page title contains 'Sphere' or 'Aastrika' | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0408 | Public Page | Public Page | Verify by clicking on " Start Today " button | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0411 | Public Page | Public Page | Verify by clicking on " Support@aastrika.org " | Medium | ✔ Done | ✔ Done | Confident match in current Playwright suite
TC-0518 | Competency Dashboard | Required | Veriy If the message " You didn't pass the assessment " when user hasn't met the required percentage | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0536 | Competency Dashboard | Job Description | Veriy If the message " You didn't pass the assessment " when user hasn't met the required percentage | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0482 | Course TOC | Module - PDF | Verify by scrolling the pdf for next and previous pages | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0483 | Course TOC | Module - PDF | Verify by pinching the pdf for zoom in and zoom out | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0484 | Course TOC | Module - PDF | Verify when pdf's at last page should get update with green tick | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0495 | Course TOC | Module - Assessment | Veriy if " Continue " button is highlighted only when user met the required percentage | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0498 | Course TOC | Module | Verify by completing the entire course should give pop up for " Completion Animation " | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0595 | Course TOC | Module - Quiz | Veriy if " continue " button is highlighted even when user not met the required percentage | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0597 | Course TOC | Module - Quiz | Veriy the required percentage is displaying as " 0% " in TOC and module tab | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0247 | Create Account | Step 3 - Name Confirmation Modal | Verify modal info icon (ⓘ) is visible | Low | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0248 | Create Account | Step 3 - Name Confirmation Modal | Verify modal displays the entered full name | High | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0249 | Create Account | Step 3 - Name Confirmation Modal | Verify "will be displayed on the certificate" message is shown | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0250 | Create Account | Step 3 - Name Confirmation Modal | "Edit name" button is visible and returns to form | High | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0252 | Create Account | Step 3 - Name Confirmation Modal | Verify name in modal reflects updates after editing | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0253 | Create Account | Step 3 - Name Confirmation Modal | Verify modal background is dimmed (overlay visible) | Low | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0254 | Create Account | Step 4 - Set Password | "Set your password" heading is visible | High | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0258 | Create Account | Step 4 - Set Password | Verify Confirm Password field has its own eye icon | Low | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0259 | Create Account | Step 4 - Set Password | "Password Requirements:" heading is visible | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0261 | Create Account | Step 4 - Set Password | Criterion "One capital letter" is listed | High | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0262 | Create Account | Step 4 - Set Password | Criterion "One number" is listed | High | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0265 | Create Account | Step 4 - Set Password | Verify too-short password fails the 8-char criterion | High | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0266 | Create Account | Step 4 - Set Password | Verify password without uppercase fails the capital-letter criterion | High | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0267 | Create Account | Step 4 - Set Password | Verify password without number fails the number criterion | High | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0269 | Create Account | Step 4 - Set Password | Verify password without lowercase still passes (if not required) | Low | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0278 | Create Account | Responsive Layout | Name Confirmation modal renders correctly on mobile | Medium | ✔ Done | — Manual only | Better suited to manual verification
TC-0279 | Create Account | Responsive Layout | Set Password screen renders correctly on mobile | Medium | ✔ Done | — Manual only | Better suited to manual verification
TC-0431 | Create Account | Create Account | Verify if the default languge is " English " | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0440 | Create Account | Create Account | Verify if the next button is highlighting when given all the valid details | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0355 | Home (Authenticated) | CNE Courses | Verify course star rating is visible on each card | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0365 | Home (Authenticated) | Info Cards | Verify "Get certified" subtitle text is visible | Low | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0395 | Home (Authenticated) | Session / Auth | Verify Home page loads only for authenticated users | Critical | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0447 | Home (Authenticated) | Home (Authenticated) | Verify if both the Whatsapp and freshchat icon appears after the loader | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0451 | Home (Authenticated) | Home (Authenticated) | Verify if all the fields are filled with valid details | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0452 | Home (Authenticated) | Home (Authenticated) | Verify after entering all the valid fields only " next " button should highlighted | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0458 | Home (Authenticated) | Home (Authenticated) | Verify after entering all the valid fields only " Done " button should highlighted | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0626 | Home (Authenticated) | Accessibility | Verify all interactive elements are keyboard-accessible | Medium | ✔ Done | — Manual only | Better suited to manual verification
TC-0627 | Home (Authenticated) | Accessibility | Verify images have meaningful alt text | Medium | ✔ Done | — Manual only | Better suited to manual verification
TC-0288 | Login | Welcome Section | Verify "Welcome!" heading is displayed | High | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0303 | Login | Create Account | "or" separator is displayed | Low | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0094 | My Courses | Page Heading & Tabs | Verify "For You" tab is visible with course count | High | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0111 | My Courses | For You Tab | Verify star rating is visible on each card (top-right) | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0116 | My Courses | For You Tab | Verify For You grid is responsive on smaller viewports | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0502 | My Courses | For You | Verify that the Designation courses should display under " For you " | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0019 | Public Page | Stats Row | Verify all 4 stat cards are visible simultaneously | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0023 | Public Page | Top Courses | Verify top course cards are displayed | Critical | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0024 | Public Page | Top Courses | Verify each course card shows 'Certificate' badge | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0025 | Public Page | Top Courses | Verify each course card shows star rating | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0031 | Public Page | CNE Courses | Verify CNE badge is shown on each card (e.g., CNE: 7.5) | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0032 | Public Page | CNE Courses | Verify star rating is shown on each CNE course card | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0033 | Public Page | CNE Courses | Verify organisation badge shown on card (e.g., Indian Nursing Council) | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0036 | Public Page | CNE Courses | Verify Hindi course cards are displayed | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0070 | Public Page | Footer - Help & Contact | Verify support email has correct mailto href | High | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0072 | Public Page | Footer - Help & Contact | Verify 'Talk to us on WhatsApp' button has valid WhatsApp link | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0074 | Public Page | Footer - Additional Links | Verify 'Aastrika Foundation: https://www.aastrika.org/' link is visible | High | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0087 | Public Page | Page Quality | Verify page load time is under 10 seconds | High | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0089 | Public Page | Page Quality | Verify page URL is correct | Medium | ✔ Done | — Manual only | Manual coverage; low automation value
TC-0090 | Public Page | Page Quality | Verify page is responsive at 1280x720 desktop viewport | High | ✔ Done | — Manual only | Better suited to manual verification

## Summary
Coverage Summary by Module
Module | Total | Automated (Done) | To Add | Confirm | Manual only
Login | 60 | 4 | 53 | 1 | 2
Course TOC | 45 | 0 | 28 | 10 | 7
Create Account | 95 | 12 | 20 | 44 | 19
Home (Authenticated) | 75 | 33 | 15 | 18 | 9
Search | 11 | 0 | 11 | 0 | 0
Account | 97 | 59 | 10 | 28 | 0
Notifications | 6 | 0 | 6 | 0 | 0
Public Page | 83 | 34 | 5 | 30 | 14
Competency Dashboard | 34 | 2 | 3 | 27 | 2
My Courses | 50 | 35 | 1 | 10 | 4
Logout | 4 | 1 | 0 | 3 | 0
TOTAL | 560 | 180 | 152 | 171 | 57